## New sites
Site location | Units completed previously | Capacity | Anticipated 2017/18 | Anticipated 2018/19 | Anticipated 2019/20 | Anticipated 2020/21 | Anticipated 2021/22 | Anticipated 2022/23 | Anticipated 2023/24 | Anticipated 2024/25 | Anticipated 2025/26
Dauncey’s Hotel, Claremont Crescent, Weston-super-Mare |  | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0
26 Bristol Road Lower, Weston-super-Mare |  | 16 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0
Queensway/Midhaven Rise, Weston-super-Mare |  | 35 | 0 | 0 | 0 | 15 | 20 | 0 | 0 | 0 | 0
Land at Wilson Gardens/Scot Elm Drive, Weston-super-Mare |  | 51 | 10 | 20 | 21 | 0 | 0 | 0 | 0 | 0 | 0
Waverley House, Clevedon |  | 21 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2-6 Bay Road, Clevedon |  | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0
Court Farm, All Saints Lane, Clevedon |  | 10 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Weston College, Somerset Square, Nailsea |  | 28 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0
Youngwood Lane, Nailsea |  | 170 | 0 | 0 | 120 | 50 | 0 | 0 | 0 | 0 | 0
Harbour Road/Gordano Gate, Portishead |  | 93 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land at Wyndham Way, Portishead |  | 35 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0
Site V2, Harbour Road, Portishead |  | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0
Land south of Cadbury Garden Centre, Congresbury |  | 21 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0
Land at Shipham Lane, Winscombe |  | 28 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0
Land adjoining Coombe Farm, Winscombe |  | 24 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0
Broadleaze Farm, Winscombe |  | 74 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0
Land at Cox’s Green, Wrington |  | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0
South of Bristol Road, Churchill |  | 41 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0
F Sweeting and Son, Station Road, Sandford |  | 16 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0
Barrow Hospital |  | 66 | 0 | 26 | 40 | 0 | 0 | 0 | 0 | 0 | 0
Barrow Hospital |  | 14 | 0 | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0
Winford Coach Station, 10 High Street, Winford |  | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  | 821 | 10 | 234 | 457 | 92 | 28 | 0 | 0 | 0 | 0

## CURRENT TRAJECTORY ALL SITES
Site location | Status at April 2017 | Relevant planning permission ref | Capacity remaining at April 2017 | Site specific details/notes | Units completed previously | Remaining capacity | Anticipated 2016/17 | Anticipated 2017/18 | Anticipated 2018/19 | Anticipated 2019/20 | Anticipated 2020/21 | Anticipated 2021/22 | Anticipated 2022/23 | Anticipated 2023/24 | Anticipated 2024/25 | Anticipated 2025/26 |  | Page number in supporting document
WESTON-SUPER-MARE
Winterstoke Village (former Weston Airfield) | Part full consent, part outline, part approved subject to legal agreement | 10/P/0756/OT2 12/P/1510/OT2 13/P/0834/RM 14/P/2723/RM 15/P/2437/RM 15/P/2570/RM 16/P/0622/RM 16/P/1842/RM | 1986 | Major strategic mixed use allocation from Core Strategy. Further details in Weston Villages Supplementary Planning Document. | 317 | 2233 | 220 | 154 | 244 | 238 | 225 | 225 | 225 | 225 | 225 | 225 | 1986 | 121
Parklands Village (former RAF Locking site) | Part full consent, part outline, part consent | 09/P/1614/F 12/P/0760/F 12/P/1266/OT2 13/P/0997/OT2 15/P/1777/RM 15/P/1646/O | 3679 | Major strategic mixed use allocation from Core Strategy. Further details in Weston Villages Supplementary Planning Document. | 250 | 3700 | 34 | 85 | 410 | 452 | 475 | 525 | 525 | 400 | 414 | 393 | 3679 | 121
Land at Atlantic Road South | Full planning permission | 14/P/1210/LDE | 23 | Carried over from North Somerset Replacement Local Plan - Site H14 | 0 | 23 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 51
Land at Milton Hill | Full planning permission | 08/P/0570/RM | 12 | Carried over from North Somerset Replacement Local Plan - Site H15 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 31
Land adjacent to Plum Tree Farm, off Summer Lane | Full planning permission | 08/P/0626/RM | 8 | Carried over from North Somerset Replacement Local Plan - Site H27 | 0 | 8 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 8 | 33
Brimbleworth Farm St Georges | Full planning permission | 11/P/2214/F | 14 | Current permission, new allocation | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 43
Scot Elm Drive | Outline planning consent | 13/P/2409/O | 72 | Current permission, new allocation | 0 | 72 | 0 | 0 | 22 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 72 | 75
Land at Wellsea Grove | Full planning permission | 14/P/0156/F | 34 | Carried over from North Somerset Replacement Local Plan | 0 | 34 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 55
Royal Pier Hotel | Full planning permission subject to legal agreement | 11/P/0006/F | 63 | Carried over from North Somerset Replacement Local Plan - Site H65 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 63 | 81
Lynton House Hotel | No current consent |  | 41 | New allocation. Capacity based on past consent | 0 | 41 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 41 | 35
The Bayside Hotel | Full planning permission | 14/P/1791/F | 15 | Current permission | 0 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 49
Westacres Caravan Park | No current consent |  | 130 | Carried over from North Somerset Replacement Local Plan - H20b. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 130 | 0 | 0 | 0 | 30 | 50 | 50 | 0 | 0 | 0 | 0 | 130 | 117
Orchard House, Ebdon Road | No current consent |  | 12 | Carried over from North Somerset Replacement Local Plan - H29. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 113
Land to the rear of Locking Road | No current consent |  | 24 | New allocation. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 163
Former Weston Library and adjacent BT building, Boulevard | Part full consent, part no current consent | 16/P/0507/F | 70 | New allocation Conversion of Weston Library (Listed buiding) 20 units. Flat development on former BT building (50 units). A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 70 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 70 | 191
Lawrence Court, Lawrence Road | Full Planning Permission | 15/P/1616/F | 14 | Current permission, new allocation | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 59
Former TJ Hughes Store, High St | No current consent |  | 18 | New allocation. Retail/restaurants on ground floor | 0 | 18 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 189
Walliscote Place | No current consent |  | 70 | New allocation. Key Town Centre site. Landmark high rise buildings may be appropriate. Demolition of former Police Station building. Conversion of Magistrate Courts (listed building). Some commerical development on the foortprint of Roselawn/Central Chambers buildings. | 0 | 70 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 185
Dolphin Square | No current consent |  | 220 | New allocation. Phase 4 of the redevelopment scheme. Includes land/buildings fronting Sea Front. Pedestrian link required between Carlton St Car Park and Oxford St Development to have regard to and relate well to Phase 3 development (leisure). | 0 | 220 | 0 | 0 | 0 | 50 | 50 | 50 | 70 | 0 | 0 | 0 | 220 | 193
Land to the west of Winterstoke Road | No current consent |  | 70 | New allocation. Loss of sports pitch needs to be addressed. Layout to have regard to industrial units to the south and railway line to the west. Access off Winterstoke Rd. 0.5 ha employment on northern boundary. Consideration of fact that site is within 5km consultation zone for Bats SAC (North Somerset and Mendip Bats Special Area of Conservation). A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 70 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 161
Land to the north of the A370, Summer Lane | Full planning permission | 10/P/1339/F | 67 | Carried over from North Somerset Replacement Local Plan - Sites H17 & M2 Consideration of fact that site is within 5km consultation zone for Bats SAC. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 89 | 0 | 44 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 115
Bridge Farm, Bristol Road | No current consent |  | 73 | Carried over from North Somerset Replacement Local Plan - Sites H63 & M4 Mixed use site to include 0.5 hectares employment Flood Zone has been reassessed and site is in Flood Zone 3 - Flood Risk Assessment sequential and exception test required. Layout to have regard to proximity of railway line. Consideration of fact that site is within 5km consultation zone for Bats SAC | 0 | 73 | 0 | 0 | 0 | 23 | 50 | 0 | 0 | 0 | 0 | 0 | 73 | 111
Birnbeck Pier | No current consent |  | 50 | New allocation for mixed use scheme. Residential, leisure, hotel and tourism, ancillary retail, cafes, bars and restaurants and community facilities. Does not include 63 dwellings on Royal Pier Hotel, Dorville or Lynton House Hotel. Prince Consort Gardens to be kept free from development. Madiera Car park has potential for development. | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 50 | -
Gas Works, Winterstoke Road | No current consent |  | 240 | New allocation. Contamination study required. Access off A370. High quality design required on key approach to Town Centre. Landmark buildings facing Drove Road roundabout. Pedestrian access to Rectors Way footpath (to the south), Newlands Road and Marchfield Way. Health and Safety Executive to be consulted. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 60 | 60 | 240 | -
Nightingale Close, Mead Vale | No current consent |  | 40 | New allocation for mixed use scheme, redevelopment to include retail, restaurant/cafe uses, 40 residential units, community uses and car parking. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 40 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 40 | 169
South of Herluin Way, Avoncrest Site | No current consent |  | 750 | New allocation for mixed use scheme to include the following Spine road with access off Aisecombe Way to the east and Winterstoke Rd to the south. Site for Primary School. Remediation work to eliminate risk of contamination. Noise buffer alongside railway line. Safeguarding of Airfield bridge link. Open Space. 2.5 ha of Employment land on western part site. | 0 | 750 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 750 | 175
Former Bournville School Site, Sellworthy Road | No current consent |  | 45 | New allocation. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 45 | 0 | 0 | 0 | 20 | 25 | 0 | 0 | 0 | 0 | 0 | 45 | 179
Former Sweat FA Site, Winterstoke Road | No current consent |  | 45 | New allocation. Vehicular and pedestrian access off Bridge Rd. Layout and design to have regard to working garage to the west. Health and Safety Executive to be consulted. Contaminated Land Assessment Required. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 45 | 0 | 0 | 0 | 20 | 25 | 0 | 0 | 0 | 0 | 0 | 45 | 181
Station Gateway | No current consent |  | 300 | New allocation. Includes Sunnyside Road, Locking Road Car Park, Station Approach and part of Tesco car park. High Quality Design on key approach to Town Centre. Design standards to be set out in Town Centre Regeneration Supplementary Planning Document. Retention of public car parking levels through multi storey development. Improved pedestrian links to and across railway station. Area included in the "area of search" for a new Primary School site. Area suitable for office development. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 300 | 0 | 0 | 0 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 300 | 165
Land at Bridgwater Road | No current consent |  | 70 | New allocation. Hedge/tree boundaries to be retained wherever possible. Highway access to be delivered south of site onto Bleadon Hill. Transport Assessment to assess safety aspects of increased vehicular and pedestrian movements at the A370 junction Consideration of fact that site is within 5km consultation zone for Bats SAC. | 0 | 70 | 0 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 70 | 171
Land north of Oldmixon Road | Outline planning consent | 16/P/0150/O | 130 | Current permission |  |  |  | 0 | 0 | 30 | 50 | 50 | 0 | 0 | 0 | 0 | 130
Land at Wentwood Drive | Outline planning consent | 15/P/0983/O | 50 | Current permission |  |  |  | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 50
Dauncey's Hotel, Claremont Crescent | No current consent |  | 10 | To be finalised |  |  |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10
26 Bristol Road Lower | No current consent |  | 16 | To be finalised |  |  |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16
Queensway/Midhaven Rise | No current consent |  | 35 | To be finalised |  |  |  | 0 | 0 | 0 | 15 | 20 | 0 | 0 | 0 | 0 | 35
Land at Wilson Gardens/Scot Elm Drive | No current consent |  | 51 | To be finalised |  |  |  | 10 | 20 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 51
CLEVEDON
Clevedon Hall Estate | Full planning permission | 12/P/1539/F 15/P/2135/F | 39 | Current permission | 0 | 42 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13
Marine Hill House, Marine Hill | Full planning permission | 11/P/2183/F | 9 | Current permission | 5 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9
Moor Lane | No current consent |  | 10 | Carried over from North Somerset Replacement Local Plan - Site H87. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | -
Yeolands Farm | No current consent |  | 15 | New Allocation. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 |  | -
North of Churchill Avenue | No current consent |  | 44 | New Allocation. Part of site to be given over to improved play/POS facilities. Access via Wordsworth Rd. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 44 | 0 | 0 | 0 | 22 | 22 | 0 | 0 | 0 | 0 | 0 |  | 131
Millcross site | No current consent |  | 70 | New Allocation. Previously proposed as a new hospital site. Site large enough to accommodate some health/care facilities. Mix of 2-3 storey development appropriate. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 70 | 0 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 |  | 129
Waverley House | Full planning permission | 17/P/0720/CUPA | 21 | Current permission |  |  |  | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2-6 Bay Road | No current consent |  | 19 | To be finalised |  |  |  | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0
Court Farm, All Saints Lane | No current consent |  | 10 | To be finalised |  |  |  | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
NAILSEA
Trendlewood Way | No current consent |  | 30 | New allocation. Was previously proposed as mixed development. Retention of wooded area fronting Trendlewood Way required. Land to be made available for local shop unit. Consideration of fact that site is within 5km consultation zone for Bats SAC. Coal Mining Risk Assessment Required. | 0 | 30 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 143
Police Station | No current consent |  | 40 | New allocation | 0 | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 133
Land at West End | No current consent |  | 10 | New allocation. Consideration of fact that site is within 5km consultation zone for Bats SAC. | 0 | 20 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 137
West of Engine Lane | No current consent |  | 183 | New allocation. Access off Engine Lane. Strong hedge boundaries to be retained. Footpath on western side of Engine Lane. Full Transport Assessment required. Replacement or improved sport facilities required. Housing mix to meet local needs. Consideration of fact that site is within 5km consultation zone for Bats SAC. | 0 | 183 | 0 | 0 | 40 | 45 | 48 | 50 | 0 | 0 | 0 | 0 | 183 | 139
Land south of The Uplands | No current consent |  | 50 | New allocation. Access off The Uplands (to be widened). Requires retention of strong hedge boundaries especially on southern boundary. Housing mix to meet local needs. Consideration of fact that site is within 5km consultation zone for Bats SAC. | 0 | 50 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 50 | 147
Land at North West Nailsea | No current consent |  | 450 | New allocation. Capacity of 450 dwellings considered a maximum. Spine Road running through site (from Pound Lane to Watery Lane) required. Pylons to be removed. Undergrounding of 132kv line on northern boundary. Transport Assessment required. New Primary School to be included as part of development. Relocation or replacement of Fryth Way sports pitch. Where possible retention of Tree Preservation Order trees. Retention of strong hedge boundaries especially to the north. PROW links to Causeway View. Coal Mining Risk Assessment required. Housing mix to meet local needs. Protection of adjacent Tickenham, Nailsea and Kenn Moor Site of Special Scientific Interest. Consideration of fact that site is within 5km consultation zone for Bats SAC. | 0 | 450 | 0 | 0 | 0 | 30 | 70 | 70 | 70 | 70 | 70 | 70 | 450 | 151
Weston College site, Somerset Square | No current consent |  | 28 |  |  |  |  | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 28
Youngwood Lane | No current consent |  | 170 |  |  |  |  | 0 | 0 | 120 | 50 | 0 | 0 | 0 | 0 | 0 | 170
PORTISHEAD
Elm Walk, Battens Orchard | Full planning permission | 17/P/0122/RM | 14 | Current permission. Capacity updated to reflect new registered application | 0 | 14 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 73
Severn Paper Mill | Full planning permission | 14/P/1186/RM | 70 | Carried over from Replacement Local Plan - Site H65 | 0 | 117 | 50 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 23
South west of Severn Paper Mill | No current consent |  | 69 | New Allocation - previously allocated employment site. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 70 | 0 | 0 | 35 | 34 | 0 | 0 | 0 | 0 | 0 | 0 |  | 155
Land south of Downside | No current consent |  | 23 | New allocation. Access through Downside. Requires retention of strong hedge boundaries and trees to the west. | 0 | 23 | 0 | 0 | 0 | 10 | 13 | 0 | 0 | 0 | 0 | 0 |  | 159
Marine View, Harbour Road | Full planning permission | 16/P/2855/F | 126 | Current consent for retirement complex | 0 | 118 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 29
Harbour Road/Gordano Gate | No current consent |  | 93 |  |  |  |  | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land at Wyndham Way | No current consent |  | 35 |  |  |  |  | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0
Site V2, Harbour Road | No current consent |  | 10 |  |  |  |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0
SERVICE VILLAGES
The Chestnuts, south of Sidcot Lane, Winscombe | Full planning permission | 16/P/1607/F | 24 | Carried over from Replacement Local Plan - Site H41 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 79
Woodborough Farm, Winscombe | Outline planning consent subject to legal agreement | 15/P/1979/O | 175 | New allocation. Main vehicular access onto Woodborough Rd. Secondary vehicular access to Church Rd. Footpath links to Strawberry line and other surrounding Public Rights of Way. Central Open Space feature. Retention of mature trees/TPO's and hedge boundaries. Consideration of fact that site is within 5km consultation zone for Bats SAC. | 0 | 175 | 0 | 0 | 25 | 50 | 50 | 50 | 0 | 0 | 0 | 0 |  | 207
Land to the east and west of Wemberham Lane, Yatton | No current consent |  | 24 | Carried over from Replacement Local Plan - Site H43. Consideration of fact that site is within 5km consultation zone for Bats SAC. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 24 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 |  | 119
Oxford Plasma, Yatton | Full planning permission | 14/P/2468/RM | 51 | Carried over from Replacement Local Plan - Site H86. Capacity updated to reflect current application. | 0 | 51 | 0 | 0 | 0 | 25 | 26 | 0 | 0 | 0 | 0 | 0 |  | 61
Arnolds Way, Yatton Phase 1 | Full planning permission | 15/P/1498/RM | 105 | Current permission. To include site for new Primary School. | 0 | 150 | 40 | 55 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 63
Yatton Station | No current consent |  | 21 | New allocation. Improved capacity of existing railway car park required as part of development proposal. | 0 | 21 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 |  | 199
Moor Lane, Backwell | Outline planning permission | 15/P/1916/O | 65 | New allocation. Vehicular access through The Briars. Landscaping/buffer strip/POS alongside railway boundary. Requires retention of strong hedge boundary to Moor Lane and on western boundary. Balancing pond required in NW corner. Consideration of fact that site is within 5km consultation zone for Bats SAC. Coal Mining Risk Assessment required. | 0 | 65 | 0 | 0 | 30 | 35 | 0 | 0 | 0 | 0 | 0 | 0 |  | 201
Cobthorn Way, Congresbury | Outline planning consent subject to legal agreement | 15/P/0519/O | 38 | Access off Cobthorn Way. Traffic Management/Calming/Pedstrian safety measures on Wrington Lane. Open Space on southern boundary. Existing hedgerows to be retained. Removal of overhead pylons. Consideration of fact that site is within 5km consultation zone for Bats SAC. | 0 | 38 | 0 | 0 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 |  | 99
Venus Street, Congresbury | Full planning permission | 16/P/0147/F | 14 | New allocation. Vehicular access onto Venus Street. | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 93
Pudding Pie Lane (West) Churchill | Outline planning consent subject to legal agreement | 15/P/2521/O | 35 | New allocation. Access off Pudding Pie Lane. Retention of existing hedgerows required. Layout to address overlooking issues from neighbouring properties. Links to Public Rights of Way on eastern boundary. Consideration of fact that site is within 5km consultation zone for Bats SAC. | 0 | 35 | 0 | 0 | 0 | 20 | 15 | 0 | 0 | 0 | 0 | 0 |  | 203
Pudding Pie Lane (East), Churchill | Outline planning consent | 15/P/1414/O | 141 | Vehicular Access off Stock Lane. Central open space. Retention of existing hedgerows required. Landscape buffer on Jubilee Lane boundary to the north. Cycleway/Pedestrian link onto Pudding Pie Lane and Stock Lane in north eastern corner of site. | 0 | 141 | 0 | 0 | 21 | 40 | 40 | 40 | 0 | 0 | 0 | 0 |  | 91
Says Lane, Churchill | Outline planning permission | 15/P/1313/O | 43 | Pedestrian crossing across A38 required. Speed limit reduction on A38. Retention of exisiting hedgerows required. Central open space feature. Swales fronting A38. Consideration of fact that site is within 5km consultation zone for Bats SAC. | 0 | 43 | 0 | 0 | 0 | 23 | 20 | 0 | 0 | 0 | 0 | 0 |  | 89
Land at North End, Yatton | Outline planning consent subject to legal agreement | 15/P/0946/O | 170 | Requires retention of exisiting hedgerows /Tree Preservation Orders. Vehicular access off roundabout. Open Space required in north eastern corner of site. Contribution required to comprehensive Surface Water Strategy. Contribution required to road safety/congestion solutions in the wider area. Consideration of fact that site is within 5km consultation zone for Bats SAC. | 0 | 170 | 0 | 0 | 20 | 50 | 50 | 50 | 0 | 0 | 0 | 0 |  | 83
Arnolds Way, (Phase 2), Yatton | Outline planning consent subject to legal agreement | 15/P/1488/O | 200 | New allocation. Requires retention of existing hedgerows. Continuation of pedestrian/cycleway links through consented housing site to the south. Footpath/Cycleway Links to Strawberry Line required. Access off roundabout through consented housing site to the south. Primary School reservation. Landscape buffer to existing development on eastern boundary. Contribution to comprehensive Surface Water Strategy. Contribution to road safety/congestion solutions in the wider area. Consideration of fact that site is within 5km consultation zone for Bats SAC. | 0 | 200 | 0 | 0 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 |  | 87
Land to the east of Wolvershill Road, Banwell | Outline planning consent subject to legal agreement | 16/P/2094/O | 44 | New allocation. Bungalows on north east corner. Limited pedestrian access to bridleway to the north. Open space through centre of site following water main. | 0 | 44 | 0 | 0 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 |  | 217
Moor Road, Yatton | No current consent |  | 60 | New allocation. Layout to respect Grange Farm (Listed Building). No development in the orchard apart from access road. Landscape Buffer alongside Stowey Rhyne. Contribution to comprehensive Surface Water Strategy. Contribution to road safety/congestion solutions in the wider area. Replacement/relocation of rugby playing pitches. Site is within 5km consultation zone for Bats SAC. | 0 | 60 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 |  | 205
Land off Wrington Lane, Congresbury | Outline planning consent | 16/P/1521/O | 50 |  |  |  |  | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0
Land south of Cadbury Garden Centre, Congresbury | No current consent |  | 21 |  |  |  |  | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0
Land at Shipham Lane, Winscombe | No current consent |  | 28 |  |  |  |  | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0
Land adjoining Coombe Farm, Winscombe | No current consent |  | 24 |  |  |  |  | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0
Broadleaze Farm, Winscombe | No current consent |  | 74 |  |  |  |  | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0
Land at Cox's Green, Wrington | No current consent |  | 28 |  |  |  |  | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land south of Bristol Road, Churchill | No current consent |  | 41 |  |  |  |  | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0
INFILL VILLAGES
Bleadon Quarry, Bleadon | Outline planning consent | 14/P/0687/O | 42 | New allocation for a mixed use scheme. 500 sq metres of employment floorspace at entrance of the site. Traffic Calming measures on Bridge Rd. Pedestrian link along Mulberry Lane. | 0 | 42 | 0 | 0 | 0 | 0 | 21 | 21 | 0 | 0 | 0 | 0 |  | 103
Jackson Barstow House, Uphill | No current consent |  | 20 | New allocation. A Flood Risk Assessment, sequential and exception test will need to accompany any planning application. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | -
Land north of Greenhill Road, Sandford | Outline planning consent | 15/P/0583/O | 118 |  |  |  |  | 0 | 25 | 43 | 50 | 0 | 0 | 0 | 0 | 0
OTHER SETTLEMENTS AND COUNTRYSIDE
Barrow Hospital, Barrow Gurney | Full Planning Permission | 13/P/0749/RM | 20 | Previously proposed to be allocated for 215 units as part of a mixed use residential and care scheme. Only consented open market dwellings retained within this allocation. | 8 | 35 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 71
Redwood Lodge, Failand | Full planning permission | 15/P/0574/F | 124 | New allocation. Only suitable for care village as consented. | 0 | 124 | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 69
Tickenham Garden Centre, Tickenham | Outline planning consent subject to legal agreement | 16/P/0032/O | 32 |  |  |  |  | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0
F Sweeting and Son site, Station Road, Sandford | No current consent |  | 16 |  |  |  |  | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0
Barrow Hospital (1), Barrow Gurney | No current consent |  | 66 |  |  |  |  | 0 | 26 | 40 | 0 | 0 | 0 | 0 | 0 | 0
Barrow Hospital (2), Barrow Gurney | No current consent |  | 14 |  |  |  |  | 0 | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0
Winford Coach Station, 10 High Street, Winford | Outline planning consent | 12/P/0390/O | 11 |  |  |  |  | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OTHER LARGE SITES WITH PLANNING PERMISSION, NOT PROPOSED TO BE ALLOCATED
Coates House, Nailsea | Prior approval change of use | 16/P/2046/CUPA | 25 | NOT PROPOSED TO BE ALLOCATED. Change of use from offices to residential | 0 | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 209
Royal Oak Public House, Nailsea | Full planning permission | 16/P/0907/F | 10 | NOT PROPOSED TO BE ALLOCATED. Erection of a building comprising 10 residential units | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 211
Weston Court, Weston-super-Mare | Prior approval change of use | 16/P/2679/CUPA | 26 | NOT PROPOSED TO BE ALLOCATED. Change of use from offices to residential | 0 | 26 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 |  | 41
Western Trade Centre, Banwell | Outline planning consent | 15/P/0968/O | 10 | NOT PROPOSED TO BE ALLOCATED. Erection of 10 dwellings | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 77
OTHER SOURCES OF SUPPLY
Small sites with planning consent (As at April 2017, minus 10% lapse rate) | [6 empty] | 94 | 117 | 117 | 118 | 118 | 118 | 0 | 0 | 0 | 0
Small site windfalls expected, based on past trend rates for plan period to date (minus 17% on garden land) | [6 empty] | 43 | 26 | 26 | 26 | 26 | 27 | 131 | 131 | 131 | 131
TOTAL DELIVERY EXPECTED | [6 empty] | 781 | 1026 | 1792 | 2529 | 2135 | 1667 | 1211 | 1001 | 1049 | 1028