## Transport
Scheme reference | Sub category | Project description | Policy context | Parish | Infrastructure category | Indicative Project cost | Status | Funding sources | Funding gap | Delivery mechanism | Project timing | Notes
TR2 | Active travel routes | Herluin Way to Locking Road Link | LP11; Schedule 7 | Weston-super-Mare | Supporting Infrastructure | c. £10m + (including highway) | Currently allocated | Development contributions/ grant funding | TBC | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service | This scheme coincides with a safeguarded major highway scheme at this location also.
TR3 | Active travel routes | Haywood Village: Moor Lane to Hutton Moor Lane | LP11; Schedule 7; DP16 Active Travel routes | Weston-super-Mare | Supporting Infrastructure | From commited planning obligations associated with Haywood Village development | Currently allocated | Development contributions/ grant funding | None identified. | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Required in line with legal agreement on Haywood Village | Part of route has already been delivered; completion due in line with planning obligations.
TR4 | Active travel routes | Haywood Village: Central route | LP11; Schedule 7; DP16 Active Travel routes | Weston-super-Mare | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Currently allocated, proposed amendment to routing in part | Development contributions/ grant funding | TBC | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Required in line with legal agreement on Haywood Village
TR5 | Active travel routes | Haywood Village: Moor Lane to A371 | LP11; Schedule 7; DP16 Active Travel routes | Weston-super-Mare | Supporting Infrastructure | From commited planning obligations associated with Haywood Village development | Proposed | Development contributions/ grant funding | None identified. | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Required in line with legal agreement on Haywood Village | Completion of this route is due in line with planning obligations.
TR6 | Extension and re-opening of railway station platforms | Weston-super-Mare railway station – bay platform re-opening | LP11; Schedule 7 | Weston-super-Mare | Supporting Infrastructure | TBC | Proposed | Various - development contributions and grant | TBC | Engagement with netwrok Rail required. | Subject to ongoing review | Engagement with GWR and other stakeholders required.
TR7 | Extension and re-opening of railway station platforms | Weston Milton railway station | LP11; Schedule 7 | Weston-super-Mare | Supporting Infrastructure | TBC | Proposed | Various - development contributions and grant | TBC | Engagement with netwrok Rail required. | Subject to ongoing review | Engagement with GWR and other stakeholders required.
TR8 | Extension and re-opening of railway station platforms | Worle railway station | LP11; Schedule 7 | Weston-super-Mare | Supporting Infrastructure | TBC | Proposed | Various - development contributions and grant | TBC | Engagement with netwrok Rail required. | Subject to ongoing review | Engagement with GWR and other stakeholders required.
TR9 | Extension and re-opening of railway station platforms | Yatton railway station | LP11; Schedule 7 | Yatton | Supporting Infrastructure | TBC | Proposed | Various - development contributions and grant | TBC | Engagement with netwrok Rail required. | Subject to ongoing review | Engagement with GWR and other stakeholders required.
TR10 | Extension and re-opening of railway station platforms | Nailsea Backwell railway station | LP11; Schedule 7 | Backwell | Supporting Infrastructure | TBC | Proposed | Various - development contributions and grant | TBC | Engagement with netwrok Rail required. | Subject to ongoing review | Engagement with GWR and other stakeholders required.
TR11 | Major Transport Scheme | Major Road Network (MRN) scheme at A38/Downside Road/West Lane | LP11; Schedule 7 | Backwell | Supporting Infrastructure | c £12-£15m to be refined through detailed design | Proposed | Various - development contributions and grant | TBC | NSC contractor | 2028/29 completion | Potential start May/June 2026 to be reviewed.
TR12 | Major Transport Scheme | Churchill crossroads, bus service improvement plan highway works | LP11; Schedule 7 | Churchill | Essential infrastructure | TBC | Proposed | BSIP grant | TBC | NSC contractor
TR13 | Railway safeguarding and future potential widening | Corridor extending 10 metres either side of the railway land boundary fence to allow for access and double track | LP11; Schedule 7 | Various | Supporting Infrastructure | TBC | Proposed | Various - development contributions and grant | TBC | Engagement with netwrok Rail required. | Subject to ongoing review | Part of Metrowest South scheme
TR14 | Railway safeguarding and future potential widening | Weston Southern Rail Chord – potential future alignment | LP11; Schedule 7 | Weston-super-Mare | Supporting Infrastructure | TBC | Proposed | Various - development contributions and grant | TBC | Engagement with netwrok Rail required. | Subject to ongoing review | Part of Metrowest South scheme
TR15 | Transport hubs at railway stations and other locations | Weston-super-Mare railway station | LP11; Schedule 7 | Weston-super-Mare | Supporting Infrastructure | TBC | Proposed | Various - development contributions and grant | TBC | Dependant upon specific scheme | Subject to ongoing review | These schemes are identified through the new local plan. Engagement with GWR and other stakeholders required.
TR16 | Transport hubs at railway stations and other locations | Weston Milton railway station | LP11; Schedule 7 | Weston-super-Mare | Supporting Infrastructure | TBC | Proposed | Various - development contributions and grant | TBC | Dependant upon specific scheme | Subject to ongoing review | These schemes are identified through the new local plan. Engagement with GWR and other stakeholders required.
TR17 | Transport hubs at railway stations and other locations | Worle railway station – including Transport Hub and railway station car park expansion | LP11; Schedule 7 | Weston-super-Mare | Supporting Infrastructure | TBC | Proposed | Various - development contributions and grant | TBC | Dependant upon specific scheme | Subject to ongoing review | These schemes are identified through the new local plan. Engagement with GWR and other stakeholders required.Part of Metrowest South scheme.
TR18 | Transport hubs at railway stations and other locations | Yatton railway station | LP11; Schedule 7 | Yatton | Supporting Infrastructure | TBC | Proposed | Various - development contributions and grant | TBC | Dependant upon specific scheme | Subject to ongoing review | These schemes are identified through the new local plan. Engagement with GWR and other stakeholders required.
TR19 | Transport hubs at railway stations and other locations | Nailsea Backwell railway station | LP11; Schedule 7 | Backwell | Supporting Infrastructure | TBC | Proposed | Various - development contributions and grant | TBC | Dependant upon specific scheme | Subject to ongoing review | These schemes are identified through the new local plan. Engagement with GWR and other stakeholders required.
TR21 | Active travel routes | Strawberry Line Extension: Clevedon/Kenn/Yatton | LP11; Schedule 9 | Kenn/ Yatton | Supporting Infrastructure | c. £6-10m | Currently allocated, proposed amendment to routing in part | Development contributions/ RIS3 funding part pending scheme viability. | TBC | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service | Various land, route alignment and access issues be to resolved. Requires additional resource to progress.
TR22 | Active travel routes | Lower Strode road to Hazel Close. Path to connect Strawberry Line to Clevedon | LP11; Schedule 10 | Clevedon | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Currently allocated | Development contributions/ grant funding | TBC | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service
TR23 | Active travel routes | Gordano Greenway: Strategic cycle link between Clevedon and Portishead | LP11; Schedule 11 | Walton-in-Gordano/ Weston-in-Gordano | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Currently considering simplified initial scheme as land negotiation likely to be very resource intensive. Little resource to progress at present. | Development contributions/ grant funding | TBC | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service | Route through Clevedon School grounds currently problematic, but aim is to be resolved in conjunction with pending redevelopment of it. Potential for part of this scheme to be facilitated by proposed residential development in Portishead - Black Rock, north of Clevedon Road.
TR24 | Major Transport Scheme | A371/Banwell Road signalisation . Required prior to development of Elborough scheme, and likely required after Phase 2 of Wolvershill Development | Wolvershill Strategic Location - Policy LP1. Unlocks 3,300 dwellings and other uses | Banwell/ Locking | Essential infrastructure | c. £800,000 | Proposed | Development contributions | No funding gap anticipated |  | Short to medium term delivery but before the Elborough residential allocation. | Proposed allocation at Elborough to fund this scheme.
TR25 | Active travel routes | Haywood Village: Cross Rhyne Bridleway to Locking Village (Winterstoke Road to Moor Lane) | LP11; Schedule 7 | Weston-super-Mare | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Proposed | Development contributions/ grant funding | TBC | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | To be delivered alongside build-out of associated development.
TR26 | Active travel routes | Haywood Village: The Runway to Haywood Village east primary school site | LP11; Schedule 8 | Weston-super-Mare | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Proposed | Development contributions/ grant funding | TBC | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | To be delivered alongside build-out of associated development.
TR27 | Active travel routes | Haywood Village: Airfield Bridge Link | LP11; Schedule 9 | Weston-super-Mare | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Currently allocated | Development contributions/ grant funding | TBC | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Likely to be longer term dependant upon overall scheme.
TR28 | Active travel routes | Haywood Village: Cross Airfield Link, The Runway | LP11; Schedule 10 | Weston-super-Mare | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | From commited planning obligations associated with Haywood Village development | Development contributions/ grant funding | None identifed | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | To be delivered alongside build-out of associated development. | Completion of this route is due in line with planning obligations.
TR29 | Active travel routes | Haywood Village: The Taxiway Hutton Moor Lane to Flowerdown Bridge | LP11; Schedule 7 | Weston-super-Mare | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Proposed | Development contributions/ grant funding | TBC | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | To be delivered alongside build-out of associated development.
TR30 | Active travel routes | Haywood Village: Future phase of development to Laneys Drove | LP11; Schedule 7 | Weston-super-Mare | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Proposed | Development contributions/ grant funding | TBC | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | To be delivered alongside build-out of associated development to the east of Haywood Village. | Connects Haywood Village Local Centre to Laneys Drove
TR31 | Active travel routes | Festival Way strategic cycle route improvements (Long Ashton, Flax Bourton, Backwell, Nailsea) | LP3: Strategic Location Nailsea and Backwell | Backwell/ Flax Bourton | Essential infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Currently allocated, proposed amendment to routing in part | Development contributions/ grant funding | TBC | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Timescale likely to be linked to delivery of development at the Nailsea and Backwell Strategic Location (Policy LP3) | This is not exhaustive, but improvements include extension of route into Nailsea town centre, extension of route alongside railway towards Nailsea & Backwell Station, crossing improvements, widening, and improvements around the Bristol boundary where provision is currently poor.
TR32 | Train station | Access improvements to Nailsea and Backwell Station | Emerging local plan Policy LP3: Nailsea and Backwell Strategic Location | Nailsea and Backwell | Supporting Infrastructure | TBC dependant on scheme | Proposed | Development contributions/ grant funding | Dependant on scheme | Scheme proposals to be developed in collaboration with Network Rail | TBC
TR33 | TBC dependant on scheme | Potential sustainable transport extension of the reserved transport corridor through the Youngwood Lane site to Station Road | LP11: Transport Infrastructure, alocations and safeguarding; LP3 Strategic Location Nailsea and Backwell | Nailsea and Backwell | Essential infrastructure | TBC dependant on scheme | Proposed | Developer funded/ delivered | None anticipated | Developer-delivered and potential for NSC role for land outside of development allocations. | Required to serve proposed development to the south of Nailsea so timing depends on the deivery of the development. | A current planning application proposes a new link road to Station Road from development south of Nailsea. This IDP makes no assumption on the suitability of this and other options may be assessed.
TR34 | Major Transport Scheme | Station Road to A370, Cross Rail Link, Nailsea | Policy LP3: Nailsea and Backwell Strategic Location | Backwell | Time-critical infrastructure | c. £30m | Proposed | Development contributions/ other | Any funding gap to be confirmed once viability testing is complete. | NSC/ developer | TBC assisted by Nailsea and Backwell Transport Study. Sections of route would be delivered as part of proposed residential development to the east of Backwell. The rail crossing would be required relatively early in the plan period to enable development south of Nailsea and other locations to progress. | Nailsea and Backwell Transport Study provides additional detail. Further studies to provide additional scheme detail including SOBC/ OBC
TR35 | Active travel routes | Clevedon to Nailsea via the Moors. Strategic cycle link between Nailsea and Clevedon | LP11; Schedule 7 | Nailsea and Clevedon | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Currently allocated | Development contributions/ grant funding | Full funding required. | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service | Requires resource to progress, but bids have been submitted to the WalkWheelCycle Trust (formally Sustrans) for feasibility and design work. Missing section of NCN33 that will connect the Festival Way to the Pier to Pier Way.
TR36 | Major Transport Scheme | Longmoor Village access road, Long Ashton | LP11; Schedule 7 | Long Ashton | Supporting Infrastructure | TBC | Proposed | TBC - development contribution. |  |  | Requirement for connection dependant upon delivery of development in Bristol administrative area
TR37 | Active travel routes | Parklands Village: A371 to Grumblepill Rhyne Route | LP11; Schedule 7 | Locking | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Currently allocated | Development contributions/ grant funding | None anticipated | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | To be delivered alongside build-out of associated development. | Important for delivery of connections to proposed Wolvershill Strategic Location.
TR38 | Active travel routes | Parklands Village: Grumblepill Rhyne Route | LP11; Schedule 7 | Banwell | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Currently allocated | Development contributions/ grant funding | None anticipated | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Planning application currently being considered for part of route. Delivery alongside ongoing build-out of Parklands Village.
TR39 | Active travel routes | Parklands Village: Locking Head Drove/ Churchlands Way to A371 | LP11; Schedule 7 | Banwell and Locking | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Currently allocated in part, proposed additional section | Development contributions/ grant funding | None anticipated | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | To be delivered alongside build-out of associated development.
TR40 | Active travel routes | Parklands Village: East to west route | LP11; Schedule 7 | Locking | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Currently allocated in part, proposed additional section | Development contributions/ grant funding | None anticipated | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | To be delivered alongside build-out of associated development.
TR41 | Active travel routes | Parklands Village: Route through Mead Fields | LP11; Schedule 7 | Banwell | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Proposed | Development contributions/ grant funding | None anticipated | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | To be delivered alongside build-out of associated development. | Mostly developed.
TR42 | Active travel routes | Parklands Village: North South Link | LP11; Schedule 7 | Banwell and Locking | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Currently allocated in part, proposed additional section | Development contributions/ grant funding | None anticipated | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | To be delivered alongside build-out of North south link highway scheme.
TR43 | Active travel routes | Parklands Village: Parklands Village to Wolvershill Link including upgrade to existing accommodation bridge | LP11; Schedule 7 | Banwell | Essential infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Proposed | Development contributions/ grant funding | None anticipated | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Required in the short-term to facilitate active link from early stages of the Wolvershill development. | Essential prior to occupation of Wolvershill.
TR44 | Active travel routes | A370_S05 Active Travel Crossing Upgrade - SW of Locking Head Drove over A370, connecting into Boundary Road | Wolvershill Strategic Location - Policy LP1. Unlocks 3,300 dwellings and other uses | Weston-super-Mare | Supporting Infrastructure | c. £450,000 | Part safeguarded in Sites and Policies Part 1. Proposed carry forward into new local plan with extended safegaurding to A371. | Development contributions collected from Parklands | None anticipated | NSC with developer contributions | Project timings under review with transport service
TR45 | Major Transport Scheme | A371 to Churchlands Way north/south link | LP11, Schedule 7 | Locking and Banwell | Time-critical infrastructure |  | Consented/ construction underway | Funded via Parklands scheme. | No funding gap anticipated | Developer delivering. | Final section being delivered 2025/26. | Northern section of route linked to proposed business park 'Parklands, West Wick roundabout'
TR48 | Major Transport Scheme | Re-opening Portishead Passenger Rail Line including new stations and parking at Portishead and Pill | Scheme safeguarded under Policy DM22: Proposed railway lines within the Sites and Policies Plan Part 1. LP11; Schedule 7. | Portishead | Essential infrastructure | TBC | Allocated | Various sources | None identified. |  | 2027/28
TR50 | Active travel routes | Strawberry Line Extension: Congresbury to Blagdon | LP11; Schedule 7 | Congresbury Churchill Wrington Burrington and Blagdon | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Proposed | Development contributions/ grant funding | TBC | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service | Would require additional resource to progress except in relation to any development proposals
TR51 | Active travel routes | Easton-in-Gordano/Pill: Marsh Lane to A369 Motorway Service Area | LP11; Schedule 7 | Pill and Easton-in-Gordano | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Proposed | Development contributions/ grant funding | TBC | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service | Would require additional resource to progress except in relation to any development proposals
TR52 | Active travel routes | Royal Portbury Dock access under M5 | LP11; Schedule 7 | Pill and Easton-in-Gordano | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Proposed | Metrowest | None identified. | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service | To be delivered as part of Metrowest works.
TR53 | Active travel routes | Royal Portbury Dock Road Underpass | LP11; Schedule 7 | Pill and Easton-in-Gordano | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Proposed | Metrowest | None identified. | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service | To be delivered as part of Metrowest works.
TR54 | Active travel routes | Marsh Lane Underpass | LP11; Schedule 7 | Pill and Easton-in-Gordano | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Proposed | Metrowest | None identified. | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service | To be delivered as part of Metrowest works.
TR55 | Active travel routes | Pill to Bristol Link along River Avon | LP11; Schedule 7 | Pill and Easton-in-Gordano | Supporting Infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Proposed | Development contributions/ grant funding | TBC | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service | Most of route owned by BCC. Initial feasibility work has taken place.
TR57 | Transport hubs at railway stations and other locations | Expansion of Long Ashton transport hub | LP11; Schedule 7 | Long Ashton | Supporting Infrastructure | TBC | Proposed | CIL, s106, grant | TBC
TR58 | Transport hubs at railway stations and other locations | Weston-super-Mare Transport Hub including coach/ lorry parking and associated services | LP11: Transport Infrastructure, alocations and safeguarding | Weston-super-Mare | Supporting Infrastructure | TBC | Proposed | CIL, s106, grant | TBC
TR59 | Major Transport Scheme | Banwell Bypass including active travel scheme | Wolvershill Strategic Location - Policy LP1. Infrastructure unlocks c. 3300 homes and other uses. LP11; Scheme included in Schedule 7. | Banwell | Time-critical infrastructure | c. £100m | Consented/ in progress | HIF/ Other/ s106 | No funding gap identified. | NSC delivery via contractor. | Completion Spring 2027 | Preparatory works underway including utilities and site preparation. Assumed contribution from Wolvershill development of c. £900k.
TR60 | Active travel routes | Flowerdown Bridge Crossing - this scheme may be integrated into TR79 scheme. | LP11; Schedule 7 | Weston-super-Mare | Essential infrastructure | Scheme costs to be confirmed through detailed design. Indicative costing are £250,000 to £1.4m per km of route | Proposed | Development contributions/ grant funding | TBC | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service | Potential contribution from Wolvershill Strategic Location.
TR61 | Bus | Bus Rapid Transport Scheme for Weston-super-Mare | LP11: Transport Infrastructure, alocations and safeguarding | Weston-super-Mare | Supporting Infrastructure | TBC | Proposed | TBC | TBC |  |  | Subject to ongoing review with transport service to identify scheme details.
TR62 | Major Transport Scheme | Herluin Way to Locking Road link, Weston-super-Mare | Scheme safeguarded under Policy DM20: Major Transport Schemes within the Sites and Policies Plan Part 1. LP11; Scheme included in Schedule 7. | Weston-super-Mare | Supporting Infrastructure | TBC | Allocated | TBC | TBC | NSC delivery via contractor. | No timescale identified. | Part of Metrowest South scheme
TR63 | Major Transport Scheme | Airfield Bridge link, Weston-super-Mare | Hayward Village - current commited site. Core Strategy CS30. DM20: Majojr Transport Scheme and new local plan LP11; Schedule 7 and DP16: major scheme and active travel scheme respectively. | Weston-super-Mare | Supporting Infrastructure | TBC | Allocated | TBC | TBC |  | No timescale identified.
TR64 | Major Transport Scheme | Future enhancements to The Runway, Weston-super-Mare | Scheme safeguarded under Policy DM20: Major Transport Schemes within the Sites and Policies Plan Part 1. LP11; Scheme included in Schedule 7. | Weston-super-Mare | Supporting Infrastructure | TBC | Allocated | TBC | TBC |  | No timescale identified.
TR65 | Major Transport Scheme | M5 J21 capacity improvements northbound -part of bridge maintenance scheme that is underway | Scheme safeguarded under Policy DM20: Major Transport Schemes within the Sites and Policies Plan Part 1. LP11; Schedule 7. | Banwell and St Georges | Time-critical infrastructure |  | Under-construction | Project funded. | No funding gap anticipated as project underway. |  | three year programme. | This scheme is funded and currently under construction.
TR66 | Major Transport Scheme | M5, J21 bypass linking Wolvershill Road to A370. Other long-term schemes associated with reducing severance and/or improving access to Strategic Road Network within the vicinity of WsM to be kept under review including through future Joint Local Transport Plans. | LP11, Schedule 7 | Banwell | Supporting Infrastructure | TBC | Allocated | TBC | Funding not identified. |  | No timescale identified but identified longer-term scheme.
TR67 | Active travel routes | A371 active travel improvements (north side) – west of M5 (Old Banwell Rd) to Summer Lane (Bypass works). | Wolvershill Strategic Location - Policy LP1. Unlocks 3,300 dwellings and other uses | Locking and Banwell | Essential infrastructure | c. £350,000 | Being progressed. | Active Travel Fund | No funding gap identified. | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service | Currently being progressed by NSC, including section west of M5 along A371, and section east of M5 via the Banwell Bypass project.
TR68 | Active travel routes | Wolvershill strategic site: Active Travel route between development and education & district centre area to Locking Parklands (Summer Lane to Grumblepill Rhyne path via M5 accommodation bridge) - scheme closely related to TR43. | Wolvershill Strategic Location - Policy LP1. Unlocks 3,300 dwellings and other uses | Banwell | Time-critical infrastructure | c. £1m | Proposed | Development contributions/ grant funding | No funding gap identified. | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service
TR69 | Active travel routes | Wolvershill strategic site: Wolvershill Road motorway bridge active travel scheme- scheme description subject to further transport modelling. | Wolvershill Strategic Location - Policy LP1. Unlocks 3,300 dwellings and other uses. LP8; Schedule 7. | Banwell | Time-critical infrastructure | c. £2m | Proposed in emerging Local Plan | Development contributions/ grant funding | No funding gap identified. | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | 2026-29 | Existing highway bridge over M5 to be upgraded to facilitate enhanced active travel connectivity between Wolvershill and WsM/ Worle train station and other destinations.
TR70 | Active travel routes | Wolvershill strategic site: Active Travel route between the development and Worle Railway Station & District Centre - Summer Lane Bridge | Wolvershill Strategic Location - Policy LP1. Unlocks 3,300 dwellings and other uses | Weston-super-Mare | Essential infrastructure |  | Proposed | Development contributions/ grant funding | No funding gap identified. | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service
TR71 | Active travel routes | Wolvershill strategic site: Wolvershill Road - works to central section of Wolvershill Rd to facilitate active travel priority (will be bus gates north and south). | Wolvershill Strategic Location - Policy LP1. Unlocks 3,300 dwellings and other uses | Banwell | Time-critical infrastructure | c. £1m | Proposed | Development contributions/ grant funding | No funding gap identified. | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | 2026-29
TR72 | Active travel routes | Traffic calming on existing Wolvershill Road alignment - interim measure prior to construction of eastern link | Wolvershill Strategic Location - Policy LP1. Unlocks 3,300 dwellings and other uses | Banwell | Time-critical infrastructure | c. £500,000 | Proposed | Development contributions/ grant funding | No funding gap identified. | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | 2026-29
TR73 | Active travel routes | Active Travel Crossing Upgrade - A370 arm of Mendip Roundabout | Wolvershill Strategic Location - Policy LP1. Unlocks 3,300 dwellings and other uses. LP8; Schedule 7. | Weston-super-Mare | Essential infrastructure | c. £450,000 | Proposed | Development contributions collected from WSL | No funding gap identified. | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | 2026-29
TR74 | Active travel routes | Wolvershill strategic site: Traffic Management to benefit active travel and equestrian use of the lanes to the east of the development; prevent motor traffic from the development accessing J21 from the east (disadvantaging traffic exiting W-s-M). | Wolvershill Strategic Location - Policy LP1. Unlocks 3,300 dwellings and other uses | Banwell | Supporting Infrastructure | c. £350,000 | Proposed | Development contributions | No funding gap identified. | Dependant on scheme - may require developer delivery on new development sites and NSC lead elsewhere | Project timings under review with transport service
TR75 | Major Transport Scheme | J21 - improve signalisation to improve operation of junction. | Wolvershill Strategic Location - Policy LP1. Unlocks 3,300 dwellings and other uses. LP8; Schedule 7. | Banwell | Time-critical infrastructure | c. £2.3m | Proposed | Development contributions | No funding gap identified. |  | 2026-29
TR76 | Active travel routes | Wolvershill Road/Churchlands Way, Weston-super-Mare - scheme to optimise the highway for active travel facilitating trips from Wolvershill to Weston-super-Mare, including Parklands. To include new crossing points from Parklands across Churchlands Way towards Kent Avenue and Scot Elm Drive. | Wolvershill Strategic Location - Policy LP1. Unlocks 3,300 dwellings and other uses. LP11; Schedule 7. | Banwell | Essential infrastructure | c. £4m | Proposed | Development contributions | Draft viability outputs |  | 2030-33
TR77 | Major Transport Scheme | A370 Somerset Avenue approach to J21. Scheme to improve capacity on approach to J21. | Wolvershill Strategic Location - Policy LP1. Unlocks 3,300 dwellings and other uses. LP11; Schedule 7. | Weston-super-Mare | Time-critical infrastructure | c. £2.7m | Proposed | Development contributions | No funding gap identified. |  | 2030-33
TR78 | Transport hubs at railway stations and other locations | Wolvershill Strategic Location Local Centre Transport Hub | Wolvershill Strategic Location - Policy LP1. Unlocks 3,300 dwellings and other uses | Banwell | Time-critical infrastructure | c£400,000 | Proposed in emerging Local Plan | Development contributions collected from WSL | No funding gap identified. | Developer/ NSC | 2026-29
TR79 | Major Transport Scheme | A370/A371 roundabout and A371/The Runway roundabout capacity improvement scheme | Wolvershill Strategic Location - Policy LP1. Unlocks 3,300 dwellings and other uses. LP11; Schedule 7. | Weston-super-Mare | Time-critical infrastructure | c. £2.6m | Proposed | Development contributions | No funding gap identified. |  | 2026-29
TR80 | Mass Transit | Mass Transit Scheme between Bristol Airport and Bristol City Centre | LP11: Transport Infrastructure, alocations and safeguarding | Various | Essential infrastructure | TBC | Joint Local Transport Plan 4 scheme | TBC - development contribution. | TBC | TBC | TBC
TR81 | Multiple | Package of schemes TBC from AECOM as part of Transport Assessment - itemised schemes will be added prior to Reg 19 consultation. | Emerging Local Plan Policy LP2 | Dundry | Time-critical infrastructure | £8528 per dwelling assumed to date. TBC based upon specific schemes and associated costs. | Proposed in emerging Local Plan | Development contributions | No funding gap identified. | Developer works | tbc
TR82 | Major Transport Scheme | Reserved transport corridor within consented Youngwood Lane site, Nailsea | LP11; Schedule 7 | Nailsea | Supporting Infrastructure | TBC | Consented | TBC | No funding gap identified.
TR83 | Major Transport Scheme | Enhancements to J20/ Ettlingen Way to increase capacity | LP11: Transport Infrastructure, alocations and safeguarding | Clevedon | Essential infrastructure | TBC | Proposed | Development contributions | TBC | NSC/ National Highways | TBC | Specific schemes to be identified - Options include signalisation, introducing a freeflow slip from Ettlingen Way to M5 northbound, and minor widening or road markings to balance lane usage and maximise capacity. Further background to this scheme requirement to be set out in Local Plan Transport Assessment
TR84 | Active travel routes | Lodway- pedestrian improvements | LP4; DP63 | Pill and Easton-in-Gordano | Supporting Infrastructure | TBC | Proposed | Development contributions | TBC |  | TBC | North Somerset Council Pill and EiG Active Travel Concept Plan
TR85 | Active travel routes | Marsh Lane - Quiet Lane / traffic calming to Portbury Docks | LP4; DP64 | Pill and Easton-in-Gordano | Supporting Infrastructure | TBC | Proposed | Development contributions | TBC |  | TBC | North Somerset Council Pill and EiG Active Travel Concept Plan
TR86 | Active travel routes | Residential streets in Pill - Improved connectivity to/from village centre and train station and on to M5 bridge | LP4; DP65 | Pill and Easton-in-Gordano | Supporting Infrastructure | TBC | Proposed | Development contributions | TBC |  | TBC | North Somerset Council Pill and EiG Active Travel Concept Plan
TR87 | Active travel routes | Connecting potential sites ‘HE2015’ and ‘HE201097’ - Bridge connection to A369 cycle path and secondary school | LP4; DP66 | Pill and Easton-in-Gordano | Essential Infrastructure | TBC | Proposed | Development contributions | TBC |  | TBC | North Somerset Council Pill and EiG Active Travel Concept Plan
TR88 | Active travel routes | Near Chapel Pill Lane - Improvements to Pill Towpath route NCN 41 | LP4; DP67 | Pill and Easton-in-Gordano | Supporting Infrastructure | TBC | Proposed | Development contributions | TBC |  | TBC | North Somerset Council Pill and EiG Active Travel Concept Plan
TR89 | Active travel routes | Pedestrian crossing improvements: Routes to Crockerne Primary School and St Katherine’s Secondary School - Pedestrian crossing improvements are proposed along routes to Crockerne Primary School, including at junctions along Lodway and Heywood Road. | LP4; DP68 | Pill and Easton-in-Gordano | Supporting Infrastructure | TBC | Proposed | Development contributions | TBC |  | TBC | North Somerset Council Pill and EiG Active Travel Concept Plan

## Education
Scheme reference | Sub category | Project description | Policy context | Parish | Priority level | Indicative Project cost | Status | Funding sources | Funding gap | Delivery mechanism | Project timing | Notes
ED1 | School playing fields | Land south of Church Lane, Backwell - primary school playing fields | LP6. Copied into Schedule 4. | Backwell | Essential infrastructure | TBC | Allocated | Owned | TBC | Depends on housing need in the area | TBC | The site is safeguarded for future use as primary school playing fields. Development should not prejudice its availability or suitability for school-related recreational use in line with the Local Plan.
ED10 | New primary school | Wolvershill Strategic Location: 420 x place Primary school including early years provision | LP1: Strategic location: Wolvershill (north of Banwell) | Banwell | Essential infrastructure | £10-12 million based on average cost per place 2022 (as per DFE school card published June 2023) | Proposed | Developer via S106 | No funding gap anticipated | Developer delivery | 2037-38 | Requirement linked to proposed housing development in Wolvershill area
ED11 | Special educational needs | Land at Ladymead Lane, Churchill - Social, Emotional and Mental Health (SEMH) school provision | LP6. Copied into Schedule 4. | Churchill | Essential infrastructure | Funded by Department for Education | Planning Committee support in December 2023, to start on site in 2026 | Department for Education | Up to £350,000 to be paid by the Council from Grant funding (approved) | Department for Education | To open in September 2027 | The site is designated for delivery of a SEMH Special Free School and should be developed in accordance with the planning application (22/P/2920/FUL) and the statutory appropriation of the land for educational purposes.
ED12 | Secondary education | Land off Smallway, Yatton - new secondary school | LP6. Copied into Schedule 4. | Yatton | Essential infrastructure | TBC - Land plus development cost of circa £40,000,000 | Proposed | CIL (and basic need contribution for land only) | TBC | North Somerset Council | TBC | Dependent on housing delivery time scales in Yatton, Backwell, Churchill and surrounding villages
ED13 | New primary school | Nailsea and Backwell Strategic Location: 420 x place Primary school east of Backwell including early years provision | LP3: Educational, sporting, leisure and community use allocations and DP63: Infrastructure Delivery and development contributions | Backwell | Essential infrastructure | £10-12 million based on average cost per place 2022 (as per DFE school card published June 2023) | Proposed | S106 | No funding gap anticipated | Developer delivery | Delivered as part of east of Backwell proposal | Requirement linked to proposed housing development in Nailsea and Backwell area
ED14 | New primary school | Nailsea and Backwell Strategic Location: 420 x place Primary school south of Nailsea including early years provision | LP3: Educational, sporting, leisure and community use allocations and DP63: Infrastructure Delivery and development contributions | Nailsea | Essential infrastructure | £10-12 million based on average cost per place 2022 (as per DFE school card published June 2023) | Proposed | S106 / CIL | No funding gap anticipated | Developer delivery | Delivered as part of south of Nailsea proposal | Requirement linked to proposed housing development to the south of Nailsea. Requires coordination across landowners, developments and promoters to produce a single masterplan for the site and optimal location of school.
ED16 | New primary school | Woodspring Strategic Location: 420 place primary school including early years provision | LP2: Woodspring Strategic Location | Long Ashton, Dundry | Essential infrastructure | £10-12 million based on average cost per place 2022 (as per DFE school card published June 2023) | Proposed | Development contributions | No funding gap anticipated | Developer delivery | TBC however first primary school expected during early phase of residential. | Potential to reduce number of primary schools if larger schools delivered- to be kept under review.
ED17 | New primary school | Woodspring Strategic Location: 420 place primary school including early years provision | LP2: Woodspring Strategic Location | Long Ashton, Dundry | Essential infrastructure | £10-12 million based on average cost per place 2022 (as per DFE school card published June 2023) | Proposed | Development contributions | No funding gap anticipated | Developer delivery | Depends on housing delivery timetable | Requirement linked to proposed housing development in Woodspring area
ED18 | New primary school | Woodspring Strategic Location: 420 place primary school including early years provision | LP2: Woodspring Strategic Location | Long Ashton, Dundry | Essential infrastructure | £10-12 million based on average cost per place 2022 (as per DFE school card published June 2023) | Proposed | Development contributions | No funding gap anticipated | Developer delivery | Depends on housing delivery timetable | Requirement linked to proposed housing development in Woodspring area
ED19 | New primary school | Woodspring Strategic Location: 420 place primary school including early years provision | LP2: Woodspring Strategic Location | Long Ashton, Dundry | Essential infrastructure | £10-12 million based on average cost per place 2022 (as per DFE school card published June 2023) | Proposed | Development contributions | No funding gap anticipated | Developer delivery | Depends on housing delivery timetable | Requirement linked to proposed housing development in Woodspring area.
ED2 | Primary school - replacement | Land next to the Village Hall, Kewstoke - replacement primary school including early years provision | LP6. Copied into Schedule 4. | Kewstoke | Supporting Infrastructure | £10-12 million based on average cost per place 2022 (as per DFE school card published June 2023) | Allocated | Developer contributions / CIL | TBC | Purchase when needed subject to developer contributions and CIL | TBC | The site is safeguarded for future school provision. Any development or use of the land should not prejudice its potential to accommodate a school in line with identified local education needs.
ED20 | Secondary education | Woodspring Strategic Location: 1400 place secondary school | LP2: Woodspring Strategic Location | Long Ashton, Dundry | Essential infrastructure | c.£40m | Proposed | Development contributions | No funding gap anticipated, although to be kept under review | Developer delivery | TBC | Need to consider arrangements for early years development whilst insufficient critcal mass to sustain a secondary school.
ED21 | New primary school | Pill Strategic Location: 420 place primary school including early years provision | LP4 Strategic Location Pill | Pill and Easton-in-Gordano | Essential infrastructure | £10-12 million based on average cost per place 2022 (as per DFE school card published June 2023) | Proposed | Development contributions | No funding gap anticipated | Developer delivery |  | Provision required on Pill Green site with contributions from all other sites in Pill.
ED3 | New primary school | Winterstoke Village east, Weston-super-Mare - new primary school including early years provision | LP6. Copied into Schedule 4. | Weston-super-Mare | Essential infrastructure | Developer funded | Planning application being processed | Developer building via S106 agreement | No funding gap anticipated | Developer delivery | To open in September 2025 | A primary school is to be delivered in line with application permitted under outline application 23/P/1669/RM.
ED4 | New primary school | Parklands Village north, Weston-super-Mare - new primary school including early years provision | LP6. Copied into Schedule 4. | Weston-super-Mare | Essential infrastructure | Developer to pay for 315 place school with SEND and Early Years facilities or equivalent | Outline consent | Developer via S106 | No funding gap anticipated | By North Somerset Council as this is a Council owned site | Depends on housing delivery timetable | A primary school is to be provided as part of the wider development permitted under outline planning permission 12/P/1266/OT2. Delivery should align with the phasing and infrastructure strategy set out in the permission and supporting Section 106 agreement.
ED5 | New primary school | Parklands Village central, Weston-super-Mare - new primary school including early years provision or pupil referral unit | LP6. Copied into Schedule 4. | Weston-super-Mare | Essential infrastructure | Developer to pay for 630 place school with SEND and Early Years facilities or equivalent | Outline consent | Developer via S106 | No funding gap anticipated | Developer delivery | Depends on housing delivery timetable | A primary school is to be provided as part of the wider development permitted under outline planning permission 12/P/1266/OT2. Delivery should align with the phasing and infrastructure strategy set out in the permission and supporting Section 106 agreement.
ED6 | New primary school | Land fronting Drove Road roundabout, Weston-super-Mare - new 420 place primary school with nursery classes including early years provision | LP6. Copied into Schedule 4. | Weston-super-Mare | Essential infrastructure | £10-12 million based on average cost per place 2022 (as per DFE school card published June 2023) | Proposed | None identified | No funding gap anticipated | Developer delivery | Depends on housing delivery timetable | The site should be retained for community use. Any development must not prejudice its potential to deliver community infrastructure in line with Local Plan policies and identified local needs.
ED7 | New primary school | Grove Farm, Backwell - new primary school including early years provision | LP6. Copied into Schedule 4. LP3 Strategic Location Nailsea and Backwell | Backwell | Essential infrastructure | Developer to provide land for a primary school with SEND and Early Years. | Consented 23/P/2618/OU2 | Development contributions from strategic sites in Backwell | TBC | TBC | Depends on housing delivery timetable | Requirement linked to proposed housing development in Nailsea and Backwell area
ED8 | New primary school | Wolvershill Strategic Location: 420 x place Primary school including early years provision | LP1: Strategic location: Wolvershill (north of Banwell) | Banwell | Essential infrastructure | £10-12 million based on average cost per place 2022 (as per DFE school card published June 2023) | Proposed/ Pre planning discussions taking place | Developer via S106 | No funding gap anticipated | Developer delivery | 2029-30 | Requirement linked to proposed housing development in Wolvershill area
ED9 | New primary school | Wolvershill Strategic Location: 420 x place Primary school including early years provision | LP1: Strategic location: Wolvershill (north of Banwell) | Banwell | Essential infrastructure | £10-12 million based on average cost per place 2022 (as per DFE school card published June 2023) | Proposed/ Pre planning discussions taking place | Developer via S106 | No funding gap anticipated | Developer delivery | 2034-35 | Depends on hosuing number, if addtitional 500 if provided then this site will be needed
ED22 | New primary school | Land at Tower Farm, Portishead - new primary school or expansion of existing if required. | LP5, Schedule 1 | Portishead | Essential infrastructure | Developer to provide land for a primary school with SEND and Early Years. | No current consent | CIL/s106 | TBC | TBC | Dependant upon build out of residential | Requirement linked to housing development in the Portishead area

## Environmental
Scheme reference | Sub category | Project description | Policy context | Parish | Priority level | Indicative Project cost | Status | Funding sources | Funding gap | Delivery mechanism | Project timing | Notes
EN1 | Coastal management | Coastal management scheme - Clevedon to Sand Bay | DP9: Flood risk | Clevedon | Essential infrastructure | TBC following completion of Coastal Mitigation Strategy | To be confirmed through Coastal Mitigation Strategy | CIL, grant, and contributions | TBC | NSC appoint contractor | Project timings TBC | A Coastal Mitigation Strategy is being prepared that will set out project scopes and timings. This will inform a programme of coastal mitigation schemes.
EN2 | Coastal management | Coastal management - ongoing maintenance of existing defences | DP9: Flood risk | Various | Essential infrastructure | TBC following completion of Coastal Mitigation Strategy | To be confirmed through Coastal Mitigation Strategy | CIL, grant, and contributions | TBC | NSC appoint contractor | Project timings TBC | A Coastal Mitigation Strategy is being prepared that will set out project scopes and timings. This will inform a programme of coastal mitigation schemes.
EN3 | Coastal management | Coastal management - future schemes | DP9: Flood risk | Various | Essential infrastructure | TBC following completion of Coastal Mitigation Strategy | To be confirmed through Coastal Mitigation Strategy | CIL, grant, and contributions | TBC | NSC appoint contractor | Project timings TBC | A Coastal Mitigation Strategy is being prepared that will set out project scopes and timings. This will inform a programme of coastal mitigation schemes.
EN4 | Coastal management | Coastal management scheme - Axe estuary banks and mouth to Uphill | DP9: Flood risk | Weston-super-Mare | Essential infrastructure | TBC following completion of Coastal Mitigation Strategy | To be confirmed through Coastal Mitigation Strategy | CIL, grant, and contributions | TBC | NSC appoint contractor | Project timings TBC | A Coastal Mitigation Strategy is being prepared that will set out project scopes and timings. This will inform a programme of coastal mitigation schemes.
EN5 | Coastal management | Coastal management scheme - Weston-super-Mare sea wall upgrade | DP9: Flood risk | Weston-super-Mare | Essential infrastructure | TBC following completion of Coastal Mitigation Strategy | To be confirmed through Coastal Mitigation Strategy | CIL, grant, and contributions | TBC | NSC appoint contractor | Project timings TBC | A Coastal Mitigation Strategy is being prepared that will set out project scopes and timings. This will inform a programme of coastal mitigation schemes.
EN6 | Coastal management | Coastal management scheme - Middle Hope car park to southern end of Beach Road Kewstoke | DP9: Flood risk | Kewstoke | Essential infrastructure | TBC following completion of Coastal Mitigation Strategy | To be confirmed through Coastal Mitigation Strategy | CIL, grant, and contributions | TBC | NSC appoint contractor | Project timings TBC | A Coastal Mitigation Strategy is being prepared that will set out project scopes and timings. This will inform a programme of coastal mitigation schemes.
EN7 | Drainage and flood risk | Wolvershill strategic site - sustainable drainage measures | LP1: Strategic location: Wolvershill (north of Banwell), and DP10: Sustainable drainage | Banwell | Time-critical infrastructure | Dependant on scheme proposed. | Proposed and required by national and local policies. | Development cost. | No funding gap anticipated | Developer implement | Delivered as required to accommodate site volumes | Requirement to avoid flood risk in River Banwell and loal rhyne network. Suds have a critical role in managing run off rates and volumes, exceeding greenfield run-off rates.
EN8 | Drainage and flood risk | Woodspring strategic site - sustainable drainage measures | LP2: Strategic location: Woodspring, and DP10: Sustainable drainage | Dundry | Time-critical infrastructure | Dependant on scheme proposed. | Proposed and required by national and local policies. | Development cost. | No funding gap anticipated | Developer implement | Delivered as required to accommodate site volumes | SuDS have a critical role in managing run off rates and volumes. Solution likely to have a key role in reservoir flood risk strategy and woder GI strategy.
EN9 | Drainage and flood risk | Nailsea and Backwell strategic site - sustainable drainage measures | LP3: Strategic location: Nailsea and Backwell, and DP10: Sustainable drainage | Nailsea and Backwell | Time-critical infrastructure | Dependant on scheme proposed. | Proposed and required by national and local policies. | Development cost. | No funding gap anticipated | Developer implement | Delivered as required to accommodate site volumes | SuDS have a critical role in managing run off rates and volumes. This may be particularly relevant on sites such as around Backwell where there are existing surface water flow paths.
EN10 | Green infrastructure | Nature Park at Nailsea and Backwell | LP3: Strategic Location Nailsea and Backwell | Backwell and Flax Bourton | Essential infrastructure | Scheme costs dependant upon size of land required | Proposed |  | No funding gap anticipated | Developer provides site and intial works. Managed by third party. |  | Evidence being analysed to identify the total quantum of land required for mitigation. May be delivered over a single or multiple sites.
EN11 | Green infrastructure | Pill strategic site - green infrastructure | LP4: Strategic Location, Pill and Easton-in-Gordano |  | Supporting Infrastructure | Part of overall development cost |  |  | No funding gap anticipated
EN12 | Green infrastructure | Wolvershill strategic site - green infrastructure | LP1: Strategic location: Wolvershill (north of Banwell), and DP34: Green infrastructure | Banwell | Supporting Infrastructure | Part of overall development cost | Proposed in emerging local plan, and Outline applications and parameter plans (subject to current assessment for suitability) | Developer funded. | No funding gap anticipated | Developer delivered as part of ground site works | Required during intial phases of development | Includes various green space typologies including ecological and play space
EN13 | Green infrastructure | Nature Park at Wolvershill - part of ecological mitigation for the proposed development | LP1: Strategic location: Wolvershill (north of Banwell), and DP34: Green infrastructure | Banwell | Essential infrastructure | Scheme costs dependant upon size of land required | Proposed | Developer funded | No funding gap anticipated | Developer provides site and intial works. Managed by third party. | Required during intial phases of development | Size of required space to be informed by Sarah Dale's work. Feature provides mitigtion for entire Wolvershill Strategic Location. Areas of grazing and appropriate licenses to be confirmed.
EN14 | Green infrastructure | Woodspring strategic site - green infrastructure | LP2: Strategic location: Woodspring, and DP34: Green infrastructure | Dundry | Supporting Infrastructure | Part of overall development cost | Proposed | Developer funded. | No funding gap anticipated | Developer delivered as part of ground site works | Required during intial phases of development | Includes various green space typologies including ecological and play space
EN15 | Green infrastructure | Nature Park at Woodspring | LP2: Strategic Location Woodspring | Dundry | Essential infrastructure | Scheme costs dependant upon size of land required | Proposed | Developer funded | No funding gap anticipated | Developer provides site and intial works. Managed by third party. | Required during intial phases of development | Evidence being analysed to identify the total quantum of land required for mitigation. May be delivered over a single or multiple sites. Feature provides mitigtion for entire Woodspring Strategic Location. Areas of grazing and appropriate licenses to be confirmed.
EN16 | Green infrastructure | Wetland at Nailsea | LP3: Strategic Location Nailsea and Backwell | Nailsea | Supporting Infrastructure | TBC | Proposed | TBC | TBC | TBC | TBC | Project supported by Nailsea Town Council.
EN17 | Green infrastructure/ noise mitigation | Wolvershill strategic site - noise bund adjacent to M5. Delivered as a multi-functional landscaped noise bund with recreational cycle route designed in. | LP1: Strategic location: Wolvershill (north of Banwell), | Banwell | Time-critical infrastructure | Part of overall development cost | Proposed in emerging local plan, and Outline application and parameter plans submitted by Wain Estates (subject to current assessment for suitability) | Developer funded. | No funding gap anticipated | Developer delivered as part of ground site works | Required during intial phases of development | Multifunctional landscaped noise bund

## Social
Scheme reference | Sub category | Project description | Policy context | Parish | Priority level | Indicative Project cost | Status | Funding sources | Funding gap | Delivery mechanism | Project timing | Notes
SO1 | Cemetary provision | Land at Mendip Road, Yatton - cemetary | LP6 Schedule 4 | Yatton | Essential infrastructure | TBC | Proposed | TBC | TBC | TBC | TBC | To be discussed with Yatton Parish Council
SO2 | Gypsy and travellor sites | Pitch provision at Wolvershill - minimum 18 pitches | Wolvershill Strategic Location - Policy LP1. | Banwell | Essential infrastructure | £90,000/ pitch | Proposed | Developer funded | No funding gap anticipated. | Developer provides land and servicing either on site or off site in alternative suitable location. | Provision of site(s) during initial phases of development programme. | Preferred to be located across smaller sites.
SO3 | Gypsy and travellor sites | Pitch provision at Woodspring - minimum 18 pitches | LP2: Woodspring Strategic Location | Dundry | Essential infrastructure | £90,000/ pitch | Proposed | Developer funded | No funding gap anticipated. | Developer provides land and servicing either on site or off site in alternative suitable location. | Provision of site(s) during initial phases of development programme. | Preferred to be located across smaller sites.
SO4 | Health | Healthcare provision at Nailsea and Backwell Strategic Location - new or enhanced | LP3: Nailsea and Backwell Strategc Location | Nailsea | Essential infrastructure | Dependant on scheme | Proposed | Development contributions / other - depends on scheme. The NHS supports Primary Care to secure funding for premises, dependant upon scheme and funding. | No funding gap anticipated. | To be determined and dependant on provision | Dependant on local circumstances. | A specific project is not yet identified however, in ight of the additional growth in Nailsea and Backwell this item reflects the likely requirement for additional capacity.
SO5 | Health | Healthcare provision at Wolvershill/ Banwell Parish - scope to deliver facility as part of the Wolvershill Local Centre and/or enhancement of existing facilities. | DP49: Healthy places; LP1: Wolvershill Strategic Location | Banwell | Essential infrastructure | Dependant on scheme | Proposed | Development contributions / other - depends on scheme. The NHS supports Primary Care to secure funding for premises, dependant upon scheme and funding. | No funding gap anticipated. | To be determined and dependant on provision | Deliered as part of phased built out of local centre and subject to service provider requirements. | The requirement for development contributions towards healthcare infrastructure from new development will be determined by working with the Integrated Care Board and other key stakeholders as appropriate, in accordance with the following process: 1. Assess the level and type of demand generated by each proposal. 2. Work with the ICB to understand the capacity of existing healthcare infrastructure and the likely impact of the site on capacity in the locality. 3. Identify appropriate options to increase capacity to accommodate additional requirements and the associated capital costs. 4. Identify the appropriate form of development contribution, which may include financial obligations, on-site infrastructure, provision of land or a combination of these.
SO6 | Health | Healthcare provision at Woodspring Strategic Location | LP2: Woodspring Strategic Location | Dundry | Essential infrastructure | Dependant on scheme | Proposed | Development contributions / other - depends on scheme. The NHS supports Primary Care to secure funding for premises, dependant upon scheme and funding. | No funding gap anticipated. | To be determined and dependant on provision | Deliered as part of phased built out of local centre and subject to service provider requirements.
SO7 | Housing type and mix | Wolvershill strategic location - extra care provision | LP1: Strategic location: Wolvershill (north of Banwell) and DP47: Older persons accommodation | Banwell | Supporting Infrastructure | TBC | Proposed and current application | Development funded | No funding gap anticipated. | Developer delivers | Short to medium terms linked to build-out of proposed local centre
SO8 | Housing type and mix | Woodspring strategic location - extra care provision | LP2: Woodspring Strategic Location | Dundry | Supporting Infrastructure | TBC | Proposed | Development funded | No funding gap anticipated. | Developer delivers | TBC
SO9 | Leisure and recreation | Swimming facilities in Nailsea and Backwell area. Contributions to upgrading and/ or new provision. | LP3: Nailsea and Backwell Strategc Location | Nailsea | Supporting Infrastructure | Dependant on scheme | Proposed | CIL/ s106/ grant | £4m-£24m dependent on scheme | NSC contracting | TBC and dependant on scheme
SO10 | Leisure and recreation | Skatepark/Wheels park: Spec to be decided, similar to existing provision in NS, an area of 2882m2 in requried with a proposed concrete skate park of around 570m2 excluding landscaping. This is a combined design that incorporates scooters, bikes and skateboards. | LP3: Nailsea and Backwell Strategc Location | Nailsea/ Backwell | Supporting Infrastructure | c. £250,000 to be determined based upon site-specific circumstancesc. | Proposed | Developer contribution | No funding gap anticipated. | NSC contracting | Inline with development occupation
SO11 | Leisure and recreation | 1 x Multi Use Games Area | LP3: Nailsea and Backwell Strategc Location | Nailsea/ Backwell | Supporting Infrastructure | £40,000-80,000 to be determined based upon site-specific circumstances | Proposed | Development contribution | No funding gap anticipated. | NSC contracting | inline with development occupation
SO12 | Leisure and recreation | Skate/ wheels park or MUGA | LP4 Pill Strategic Location | Pill and Easton-in-Gordano | Supporting Infrastructure | c. £40,000-250,000 dependant on scheme and to be determined based upon site-specific circumstances | Proposed | Development contribution | No funding gap anticipated. | NSC contracting | Inline with development occupation
SO13 | Leisure and recreation | Wolvershill community space provision within local centre/ including sport and leisure facilities | LP1: Strategic location: Wolvershill (north of Banwell), | Banwell | Essential infrastructure | TBC | Proposed | Development contribution | No funding gap anticipated. | To be delivered in early phases of development in consultation with parish council and other potential occupants. | Delivered within initial 5 years of development commencing. | Community space and mobility hub required during first phases of local centre development. The community hall will consist of internal space of 600m2 to include height for 2 x badminton court and perhaps incorporate basketball, netball, indoor football. Separate scope for meeting and social activity space with a fully equipped kitchen, toilets, additional storage space and adequate circulation allowance to ensure the facility is fully accessible. Design advice and guidance would be agreed by North Somerset Leisure and would follow Sport England Guidelines for Village/Community Halls (attached). A sum of £60k towards fit out and equipment for the community hall facility plus a total commuted sum of £50,000 for a period of up to 5 years to enable the community or management organisation to form a sustainable facility. For effective management and maximum usage this facility should be sited in the same location as the pitches so that adequate car parking and changing facilities to accommodate the following pitch requirement can be integrated into the building.
SO14 | Leisure and recreation | Skatepark/Wheels park: Spec to be decided, similar to existing provision in NS, an area of 2882m2 in requried with a proposed concrete skate park of around 570m2 excluding landscaping. This is a combined design that incorporates scooters, bikes and skateboards. | LP1: Strategic location: Wolvershill (north of Banwell), | Banwell | Supporting Infrastructure | c. £250,000 to be determined based upon site-specific circumstancesc. | Proposed | Development contribution | No funding gap anticipated. | NSC contracting | Inline with development occupation | Spec to be decided but similar to Portishead Wheels and Skate park which occupies an area of 2882m2 with a proposed concrete skate park of around 570m2 excluding landscaping. This is a combined design that incorporates scooters, bikes and skateboards.
SO15 | Leisure and recreation | Pitches 2x adult and 2x junior | LP1: Strategic location: Wolvershill (north of Banwell), | Banwell | Supporting Infrastructure | c. £150,000 per adult pitch and £75,000 per junior pitch. £75,000 commuted sum per pitch. | Proposed | Development contribution | No funding gap anticipated. |  | Inline with development occupation | 2 x adult grass pitches (one to be floodlit to meet FA requirement for fixtures). As the pitches are positioned within the green space we will not require floodlighting to enhance the area for wildlife and biodiversity. 2 x junior grass football . Pitches to be laid to high STRI standard, drained and provided with accompanying changing facilities (see above) and comply with technical guidance on the FA website. Each pitch will require a commuted sum to cover a period of 15 years maintenance this will be agreed at a later date as figures are subject to indexation each year The small clubhouse for changing facilities/storage at the outdoor space will need to be built to FA standard and low level lighting for the parking will need to be considered for security and health and safety The specification and design should be agreed in conjunction with NSC Leisure team before delivery of the scheme.
SO16 | Leisure and recreation | Tennis Courts x 3 | LP1: Strategic location: Wolvershill (north of Banwell), | Banwell | Supporting Infrastructure | c. £150,000 to be determined based upon site-specific circumstances | Proposed | Development contribution | No funding gap anticipated. | NSC contracting | Inline with development occupation | Three outdoor tarmac tennis courts to Sport England standards. Floodlit, with 3m fencing and installed with LTA approved automatic gate access system. This system along with online booking system is convenient and easily managed by the community or trust and means that residents have access to good quality provision A commuted sum will be required, amount to be discussed but will cover up to 15 years.
SO17 | Leisure and recreation | 1 x Multi Use Games Area | LP1: Strategic location: Wolvershill (north of Banwell), | Banwell | Supporting Infrastructure | £40,000-80,000 to be determined based upon site-specific circumstances | Proposed | Development contribution | No funding gap anticipated. | NSC contracting | Inline with development occupation | 1 x Multi Use Games Area. 34mx24m – with a porous macadam surfacing, 50mm base course and 25mm wearing course with a suitable compacted stone base. The MUGA needs to have 3m high football and basketball goals, 2m high end fencing, 1m high side fencing. Must include cricket wicket panels and chicane entrance, lean back benches for spectators and line markings for football, basketball and netball. This would be best located next to a community hall and a commuted sum to be confirmed is required for the MUGA to cover a period of 15 years.
SO18 | Leisure and recreation | Woodspring community space provision within local centre utlising exisitng Golf Club House - may overlap with SO19 | LP2: Woodspring Strategic Location | Dundry | Essential infrastructure | TBC | Proposed | Development contribution | No funding gap anticipated. | To be delivered in early phases of development in consultation with parish council and other potential occupants. | Community space required to be open by 2029 | Community space to utilise the existing Club House and can be delivered early in the programme.
SO19 | Leisure and recreation | Community hall with an emphasis on fitness and multi activity including meeting space and storage. The community hall will consist of internal space of 600m2 to include height for 2 x badminton court and perhaps incorporate basketball, netball, indoor football. | LP2: Woodspring Strategic Location | Dundry | Essential infrastructure | TBC | Proposed | Development contribution | No funding gap anticipated. |  | TBC | Separate scope for meeting and social activity space with a fully equipped kitchen, toilets, additional storage space and adequate circulation allowance to ensure the facility is fully accessible. Design advice and guidance would be agreed by North Somerset Leisure and would follow Sport England Guidelines for Village/Community Halls (attached).
SO20 | Leisure and recreation | 2 x adult grass pitches (one to be floodlit to meet FA and/or RFU requirement for fixtures). | LP2: Woodspring Strategic Location | Dundry | Essential infrastructure | c. £150,000 per adult pitch and £75,000 commuted sum per pitch. | Proposed | Development contribution | No funding gap anticipated. | NSC contracting | Inline with development occupation | Pitches to be laid to high STRI standard, drained and provided with accompanying changing facilities (see above) and comply with technical guidance on the FA/RFU website. The changing rooms need to be accessible from the inside and outside with the ability to be locked from the main building (if located as part of the community hall site). Additional maintenance and equipment storage
SO21 | Leisure and recreation | 2 x junior grass football pitches | LP2: Woodspring Strategic Location | Dundry | Essential infrastructure | c. £75,000 per junior pitch. £75,000 commuted sum per pitch. | Proposed | Development contribution | No funding gap anticipated. | NSC contracting | Inline with development occupation
SO22 | Leisure and recreation | Tennis Courts x 3 | LP2: Woodspring Strategic Location | Dundry | Essential infrastructure | c. £150,000 to be determined based upon site-specific circumstances | Proposed | Development contribution | No funding gap anticipated. | NSC contracting | Inline with development occupation | Three outdoor tarmac tennis courts to Sport England standards. Floodlit, with 3m fencing and installed with LTA approved automatic gate access system. This system along with online booking system is convenient and easily managed by the community or trust and means that residents have access to good quality provision A commuted sum will be required, amount to be discussed but will cover up to 15 years.
SO23 | Leisure and recreation | 1 x Multi Use Games Area | LP2: Woodspring Strategic Location | Dundry | Essential infrastructure | c. £40,000-60,000 to be determined based upon site-specific circumstances | Proposed | Development contribution | No funding gap anticipated. | NSC contracting | Inline with development occupation | 34mx24m – with a porous macadam surfacing, 50mm base course and 25mm wearing course with a suitable compacted stone base. The MUGA needs to have 3m high football and basketball goals, 2m high end fencing, 1m high side fencing. Must include cricket wicket panels and chicane entrance, lean back benches for spectators and line markings for football, basketball and netball.
SO24 | Leisure and recreation | Skatepark/Wheels park: Spec to be decided, similar to existing provision in NS, an area of 2882m2 in requried with a proposed concrete skate park of around 570m2 excluding landscaping. This is a combined design that incorporates scooters, bikes and skateboards | LP2: Woodspring Strategic Location | Dundry | Essential infrastructure | c. £250,000 to be determined based upon site-specific circumstancesc. | Proposed | Development contribution | No funding gap anticipated. | NSC contracting | Inline with development occupation
SO25 | Leisure and recreation | Maltlands, Railway Triangle, Locking Castle, Weston-super-Mare - Allotments | LP6 Schedule 4 | Weston-super-Mare | Supporting Infrastructure | TBC | Allocated | CIL/ s106 |  |  | TBC
SO26 | Leisure and recreation | Land adjacent to village hall, Portbury - car park | LP6 Schedule 4 | Portury | Supporting Infrastructure | TBC | Allocated | Development contribution |  |  | TBC
SO27 | Leisure and recreation | Provision to include 600m2 multi-functional community/sports hall, two adult grass playing pitches with changing facilities, two outdoor tennis courts laid to the relevant standards, multi-use games area and neighbourhood equipped area for play. Design, layout and specifications of all facilities to be agreed with the Council. | LP6 Schedule 4 | Weston-super-Mare | Essential infrastructure | TBC | Subject to Outline consent as part of Parklands scheme | Development contribution | No funding gap anticipated. |  | TBC

## Utilities
Scheme reference | Sub category | Project description | Policy context | Parish | Priority level | Indicative Project cost | Status | Funding sources | Funding gap | Delivery mechanism | Project timing | Notes
UT1 | Waste | Weston-super-Mare - replacement waste transfer station | DP32: Waste management facilities | Weston-super-Mare | Time-critical infrastructure | TBC | Proposed | Capital | TBC | Design and Build | c.2027 - 2029 construction phase
UT2 | Waste | Backwell - waste transfer station relocation and enhancement of other centres as required related to additional capacity requirements. | DP32: Waste management facilities | Backwell | Essential infrastructure | TBC | Project initiation | TBC | TBC | TBC | TBC | General requirement to improve other centres in North Somerset as a result of population growth. Ongoing review of requirements.
UT3 | Utilities | Utilities infrastructure incluidng water, gas, electricity, digitial infrastructure to be kept under review. | DP63: Infrastructure delivery and development contributions | Various as required | Essential infrastructure | Dependant on project | As required. | Developer funded. | n/a | Combination of direct delivery by developer and/or service provider. | Aligned to development programme. | Necessary upgrades carried out once specific development proposals are developed.
UT4 | Renewable energy | Renewable energy generation | DP7: Renewable and low carbon energy | Various where suitable | Essential infrastructure | Item includes various projects with varying cost | Ongoing | Primarily delivered on-site in conjuction with development. Grant funding sources to be explored to deliver additional schemes | No gap considered as commercial case for proposals required.
UT5 | Emergency services | Upgrades to infrastructure as a result of new development e.g. fire hydrants | DP63: Infrastructure delivery and development contributions | Various | Essential infrastructure | Dependant on reqirements and scheme. |  | Development contributions | None antipipated | Developer provides during construction | In line with development