## Instructions
Guidance on completing the 2025/26 Delivery Plan template
Header: The name of the LTA (or LTAs) should be added so that the header reads "ANYTOWN COUNCIL BUS SERVICE IMPROVEMENT DELIVERY PLAN 2025/26"
Category of scheme/measure: should be chosen from the drop-down list in the spreadsheet cell. If a scheme falls into more than one category then category under which the majority of benefits arise should be selected. If that is not possible, classify the scheme as 'Other' and then provide an explanation in the 'Additional Description' field. Alternatively, consider whether the scheme is a single scheme.
Name of scheme/measure: must capture the essentials of what it is and where it is (where appropriate) without being too long or too short, for example 'High St Anytown bus lane', 'Anytown area all-operator weekly ticket'. Scheme names used should be identifiable against the names used in the 2024 BSIP document and (where appropriate) the EP Scheme and, for schemes using previous years' BSIP funding, the scheme names that have been used throughout programme delivery reporting to date. Having said this, the opportunity can be taken to refine/improve names to add useful detail on what and where the scheme or measure is. All bus service improvement schemes and measures which will be delivered in 2025/26 or 2026/27 should be listed, including schemes which are being funded from previous years' DfT BSIP funding or any other funding source - the scheme funding mix should be clarified in the appropriate columns. For capital schemes, all schemes that will be started or completed and opened in 2025/26 should be listed. Schemes in the 2024/25 programme which have been completed and opened, and on which there will be no further spending in 2025/26 should not be listed. For revenue schemes, all schemes that will be or are planned to be running in 2025/26 or 2026/27 should be listed. This should include bus service support schemes that will be spending previous years' DfT BSIP funding.
Additional description of scheme/measure (including intended beneficial outcomes): this field is for useful additional description of the scheme/measure that is not captured in the scheme name. This description is an opportunity to describe the scheme outputs (for example, "200m bus lane on High St Anytown plus traffic signals bus detection and priority at High St/Market St saving on average 20 seconds per bus and up to 5 mins per bus at time of peak traffic congestion on corridor carrying 8 buses/hour"; "£5 discount on £17 commercial fare for all-operator weekly ticket covering all services in the Anytown area bus network"). It should also contain an initial assessment of the intended beneficial outcomes from the scheme or measure. To the maximum extent possible, these should be quantified. For example, "The High St Anytown bus lane aims to save 200 minutes of bus delay time per week, and improve punctuality on routes 2, 7 and 87A by 5 percentage points." Or, "Target is sales of 10,000 Anytown all-operator weekly tickets per 4 week period, saving passengers £650k per year". The description of the intended beneficial outcomes should describe how the scheme/measure contributes towards delivery of the objectives of the 2024 BSIP.
Target delivery date: For capital schemes, this should be the date the scheme (infrastructure or equipment) is commissioned and opens for use by the public. For revenue schemes: This should be the date the scheme commences e.g. the date a fares scheme or bus service contract is live and in use by passengers. This target date will be the baseline for subsequent quarterly monitoring and reporting. For funding allocated in 2022-23, 2023-24 and 2024-25, through Phases 1, 2 and 3 of the BSIP Programme, the specified period is March 2025 for fares schemes; and March 2026 for all other revenue schemes (e.g. service support) and all capital schemes. For Bus Grant funding allocated in this letter, the specified period means March 2027 for all schemes, both revenue and capital. We strongly encourage you to use the Bus Grant funding by March 2026 in order to deliver benefits to passengers and communities as quickly as possible. We recognise, however, that it will not always be fully possible to do so, or to do so in a value for money manner, given the lead times on capital projects and usual lengths of tendered bus service contracts. Where absolutely necessary funding can therefore be carried forward into 2026/27. As the Department cannot provide funding in advance of need this is only appropriate where you are satisfied that without having received the payment in 2025/26 your Authority would not have been able to progress Delivery Plans or enter into contracts (either in absolute terms or at an appropriate cost and value for money). In all cases we would expect a contractual or other significant commitment to have been entered into for the full use of the funding by March 2026. You should maintain a clear record of the rationale, and where relevant VfM or cost benefits achieved, and decisions to use this funding beyond 2025/26 – which should be signed off by your Chief Finance Officer (or equivalent). A copy of any such record should be submitted with your next quarterly return when it is created or amended.
Budget/estimated cost columns: These columns should be £k numbers, separating out capital and revenue funding. (In the majority of cases it is expected that the scheme funding will either be all capital or all revenue funding.) The funding of the total scheme cost should be broken down into that finded by 2025/26 DfT Bus Grant for Local Authorities, previous years' DfT BSIP funding, and all other funding sources. The final column should be used to identify the other funding sources (DfT or other).

## Delivery Plan
North Somerset Council - Bus Service Improvement Delivery Plan 2025-26
Category of scheme/measure [select from drop down list] | Name of scheme/measure | Additional description of scheme/measure (including intended beneficial outcomes) | Target delivery date | Budget/estimated cost (£k) |  |  | (of which) 2025-26 Bus Grant (£k) |  |  | (of which) previous years' DfT BSIP funding (£k) |  |  | (of which) Other funding (£k) |  |  | Notes on other funding sources (identifying non-BSIP funding)
|  |  |  | Capital | Revenue | Total | Capital | Revenue | Total | Capital | Revenue | Total | Capital | Revenue | Total
Bus priority infrastructure | A38 Churchill Signals | Details of all schemes provided previously for BSIP1 | 2026-10-31 | 3860599.5252 |  | 3860599.5252 |  |  | 0 | 3860599.5252 |  | 3860599.5252 |  |  | 0
Bus priority infrastructure | A38 Barrow Gurney - COMPLETED |  | 2023-07-28 | 0 |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0
Bus priority infrastructure | A38 Lime Kiln Roundabout |  | 2026-04-30 | 1800646.7388 |  | 1800646.7388 |  |  | 0 | 1800646.7388 |  | 1800646.7388 |  |  | 0
Bus priority infrastructure | A38 corridor traffic signal improvements (2 junctions) |  | 2025-10-31 | 14525 |  | 14525 |  |  | 0 | 14525 |  | 14525 |  |  | 0
LTA delivery/admin costs | ANPR back office systems and processes (district wide) - COMPLETED |  | 2024-09-30 | 0 |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0
Other infrastructure | Arboricultural works (district wide) |  | 2026-03-31 | 14774 |  | 14774 |  |  | 0 | 14774 |  | 14774 |  |  | 0
Bus priority infrastructure | Existing bus lane review (district wide) |  | 2026-03-31 | 42825 |  | 42825 |  |  | 0 | 42825 |  | 42825 |  |  | 0
Bus priority infrastructure | B3133 / Southern Way / Central Way |  | 411203 | 53019 |  | 53019 |  |  | 0 | 53019 |  | 53019 |  |  | 0
Bus priority infrastructure | Ettlingen Way roundabout (M5 J20) |  | 2026-11-30 | 899933 |  | 899933 |  |  | 0 | 899933 |  | 899933 |  |  | 0
Bus priority infrastructure | Tickenham Road / Northern Way / All Saints roundabout - Closing Off Works |  | 2026-01-31 | 128295 |  | 128295 |  |  | 0 | 128295 |  | 128295 |  |  | 0
Bus priority infrastructure | Clevedon traffic signal improvements (4 junctions) |  | 2026-03-31 | 71267 |  | 71267 |  |  | 0 | 71267 |  | 71267 |  |  | 0
Bus priority infrastructure | Parking restrictions (district wide) |  | 2026-03-31 | 29345 |  | 29345 |  |  | 0 | 29345 |  | 29345 |  |  | 0
Bus priority infrastructure | A369 Portbury Hundred - REMOVED FROM PROGRAMME |  | n/a | 0 |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0
Bus priority infrastructure | A369 Martcombe Road (Phase 1) |  | 2026-09-30 | 1196513 |  | 1196513 |  |  | 0 | 1196513 |  | 1196513 |  |  | 0
Bus priority infrastructure | A369 Beggar Bush Lane - COMPLETED |  | 2023-09-30 | 0 |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0
Bus priority infrastructure | A369 Rownham Hill |  | 2026-02-28 | 422415 |  | 422415 |  |  | 0 | 422415 |  | 422415 |  |  | 0
Bus priority infrastructure | A369 corridor traffic signal improvements (3 junctions) |  | 2025-10-31 | 23451 |  | 23451 |  |  | 0 | 23451 |  | 23451 |  |  | 0
Bus priority infrastructure | WSM Routes - Worle High Street |  | 2026-11-30 | 1192123 |  | 1192123 |  |  | 0 | 1192123 |  | 1192123 |  |  | 0
Bus priority infrastructure | Uphill roundabout - REMOVED FROM PROGRAMME |  | n/a | 0 |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0
Bus priority infrastructure | WsM Interchange |  | 2026-03-31 | 50022 |  | 50022 |  |  | 0 | 50022 |  | 50022 |  |  | 0
Bus priority infrastructure | WsM traffic signal improvements (9 junctions) |  | 2025-10-31 | 123857 |  | 123857 |  |  | 0 | 123857 |  | 123857 |  |  | 0
Bus priority infrastructure | Queensway Worle / A370 B3440 |  | 2027-01-31 | 8292625.7384 |  | 8292625.7384 |  |  | 0 | 8292625.7384 |  | 8292625.7384 |  |  | 0
Bus priority infrastructure | A370 Smallway junction |  | 2026-10-31 | 2219928 |  | 2219928 |  |  | 0 | 2219928 |  | 2219928 |  |  | 0
Bus priority infrastructure | A370 Wood Hill junction - COMPLETED |  | 2024-11-30 | 0 |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0
Bus priority infrastructure | A370 Brockley Combe - Safety Audit |  | 2027-03-31 | 250000 |  | 250000 | 250000 |  | 250000 | 0 |  | 0 |  |  | 0
Bus priority infrastructure | A370 Backwell Signals |  | 2026-04-30 | 313798 |  | 313798 |  |  | 0 | 183089 |  | 183089 | 130709 |  | 130709 | S106 for adjacent works
Bus priority infrastructure | A370 Long Ashton Bypass - COMPLETED |  | 2023-04-12 | 0 |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0
Bus priority infrastructure | A370 corridor traffic signal improvements (12 junctions) |  | 2026-03-31 | 211769 |  | 211769 |  |  | 0 | 211769 |  | 211769 |  |  | 0
Bus stops/stations/interchanges | Portishead Hub |  | 2026-07-31 | 877097 |  | 877097 | 877097 |  | 877097 | 0 |  | 0 |  |  | 0
Bus stops/stations/interchanges | Clevedon Hub |  | 2026-03-31 | 824026 |  | 824026 | 9320 |  | 9320 | 814706 |  | 814706 |  |  | 0
Bus stops/stations/interchanges | Worle Terminus Hub |  | 2026-03-31 | 1270826 |  | 1270826 |  |  | 0 | 1270826 |  | 1270826 |  |  | 0
Bus stops/stations/interchanges | Nailsea Hub |  | 2026-03-31 | 531572 |  | 531572 |  |  | 0 | 531572 |  | 531572 |  |  | 0
Bus stops/stations/interchanges | Bus stop improvements |  | 2026-03-31 | 2467498 |  | 2467498 |  |  | 0 | 2217498 |  | 2217498 | 250000 |  | 250000 | S106 allocations for bus stops
Bus stops/stations/interchanges | Smaller hubs (district wide) |  | 2026-11-30 | 3156787 |  | 3156787 |  |  | 0 | 3156787 |  | 3156787 |  |  | 0
Other infrastructure | First & Last mile - ped & cycle |  | 2026-03-31 | 90296 |  | 90296 |  |  | 0 | 90296 |  | 90296 |  |  | 0
Ticketing equipment/systems | Initiative D1 Supporting the transition to digital ticketing - COMPLETED |  | 2024-06-01 | 0 |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0
LTA delivery/admin costs | Monitoring & Evaluation (excluding scheme specific costs) - COMPLETED |  | 2025-08-31 | 0 |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0
Bus stops/stations/interchanges | Shelter and stop programme – new assets | Next phase of delivery to improve, renew or create new and improved assets. Note 130 of the highest priority locations have been programmed for delivery in BSIP1.New stops and shelters cost c.£30k per stop inc. shelter and civils. This provides for an additional c.10 locations. | 2026-09-30 | 300000 |  | 300000 | 300000 |  | 300000 | 0 |  | 0 |  |  | 0
Bus stops/stations/interchanges | Shelter and stop programme – branding and improved assets | Branding and refurbishment programme sees existing stop and shelters cleaned, provided with new glass and repaired as needed. All stops will be WEST rebranded. BSIP1 funding provided for activity at 210 sites. Cost is c.£800 per site so this allows us to deliver at 250 new locations. | 2026-09-30 | 200000 |  | 200000 | 200000 |  | 200000 | 0 |  | 0 |  |  | 0
Improved information, marketing | Bus stop Real time information system updates and improvements | Additonal 10 'Eink' RTI displays at high patronage stops. | 2026-03-31 |  | 50000 | 50000 |  | 50000 | 50000 |  |  | 0 |  |  | 0
Bus stops/stations/interchanges | Rebranding | Further regional WEST branding of bus stop passenger infrastructure | 2026-03-01 |  | 50000 | 50000 |  | 50000 | 50000 |  |  | 0 |  |  | 0
Other | Behaviour change and engagement activity | Transport Decarbonisation program officer, leading regional community and stakeholder engagement program, includes, business enagement and personalised travel planing along key bus corridors and communities. | 2026-03-01 |  | 60000 | 60000 |  | 60000 | 60000 |  |  | 0 |  |  | 0
Improved information, marketing | Marketing and promotion inc ticketing promotions | Tageted package of promotions and engagement to increase patronage on essential services (6,7,9) in WSM that are yet to achieve commercial sustainability post pandemic. | 2026-03-01 |  | 50000 | 50000 |  | 50000 | 50000 |  |  | 0 |  |  | 0
Development of future proposals | Feasibility and testing. | Enables the development, testing and design of new schemes inlcuding A38 from Weston-super-Mare and Locking Road corridor. RIF to be refunded from future capital allocations and grants to provide a rolling sum for development of schemes. | 2026-03-31 |  | 400000 | 400000 |  | 400000 | 400000 |  |  | 0 |  |  | 0
Safety and security | Passenger infrastructure | CCTV delivery in WsM Interchange. Establishing a Software platform and associated monitoring costs, mixed Captial and Revenue project. | 2026-03-01 |  | 75000 | 75000 |  | 75000 | 75000 |  |  | 0 |  |  | 0
Bus stops/stations/interchanges | First and Last mile access improvements | to provide access to bus stops where there are historic internventions required such cycle parking and footway modifications. | 2026-03-01 |  | 50000 | 50000 |  | 50000 | 50000 |  |  | 0 |  |  | 0
Simpler/more affordable fares | Fares packages | Care leavers free travel package 1 year ext and age entitlement increase to 25 | 2025-04-01 |  | 140000 | 140000 |  | 140000 | 140000
Simpler/more affordable fares | Fares packages | Avon Day rider ticket cap at £7 | 2025-04-01 |  | 107000 | 107000 |  | 107000 | 107000
Simpler/more affordable fares | Fares packages | 1 year ext of £1 child ticket | 2025-04-01 |  | 180255 | 180255 |  | 180255 | 180255
Simpler/more affordable fares | Fares packages | Disabled 24/7 travel | 2025-04-01 |  | 17000 | 17000 |  | 17000 | 17000 |  |  | 0 |  |  | 0 | increased to reflect new scheme costs
LTA delivery/admin costs | Resources - staff and M&E | Staff and staffing including BSIP Programme Manager, Comms and Monitoring & Evaluation resourcing | 2026-03-31 |  | 150000 | 150000 |  | 150000 | 150000 |  |  | 0 |  |  | 0 | spent.
Bus service support/network development | Supported and Enhanced Services | X1,X4,X5,X6,X7,W7,W6,126 | 2026-03-31 |  | 2769042 | 2769042 |  | 355142 | 355142 |  | 2413900 | 2413900 |  |  | 0 | Bus grant funding reallocated to Fares, increased spend on previous years BSIP funding.
Bus service support/network development | Socially necessary bus services | 125 /125s socially necessary bus service | 2025-04-01 |  | 121190 | 121190 |  | 68153 | 68153 |  | 0 | 0 |  | 53037 | 53037 | Restianed revenue £53037, BSOG £68153
Bus service support/network development | Socially necessary bus services | X11 W9 1S socially necessary bus services | 2025-04-01 |  | 320608 | 320608 |  | 220608 | 220608 |  | 100000 | 100000 | 0 | 0 | 0
Bus service support/network development | A38 Bus corridor improvement (U2) | mulitagncy sponsored bus service, with Bristol Univeristy, WSM college and north Soemrset council to extend the U2 bus service from Langford to WSM, utilising the new bus infrastructure along the A38 corridor. | 2026-09-01 |  | 150000 | 150000 |  | 150000 | 150000 |  | 0 | 0 | 0 | 0 | 0
Bus service support/network development | Integrated Transport Solutions Transformation (developing in hous bus fleet, and delivery model, phase 1 DRT Delivery / Transformation project | Includes funding for feasibility and business case development, depot base and vehicle purchase to enable integrated bus / DRT service operations. Subject to legislation update, and final business case. | 2026-03-31 |  | 874930 | 874930 |  | 874930 | 874930 |  |  | 0 |  |  | 0
Other infrastructure | Arboricutlutral works | Clearance of obstruction to facilitate new bus routing of services 9, and X10. | 2026-03-31 |  | 35000 | 35000 |  | 30000 | 30000 |  |  | 0 |  | 5000 | 5000 | retained revenue budget for repairs and maintenance of network infrastructure
Bus service support/network development | Real Time Information system updates and renewal | Resources to tender and secure new RTI back office system, current system undermining consumer confidence due to innacurate reporting at roadside, and expires April 2026. | 2026-03-31 |  | 140000 | 140000 |  | 100000 | 100000 |  |  | 0 |  | 40000 | 40000 | £40000 retianed revenue funding for RTI systems.
Other | EP management resource | Capability and Capacity0 | 2025-04-01 |  | 63000 | 63000 |  | 63000 | 63000 |  | 0 | 0 |  | 0 | 0 | Staff resource dedicated to EP joint management with the WEMCA
|  |  |  | 30929833.0024 | 5803025 | 36732858.0024 | 1636417 | 3191088 | 4827505 | 28912707.0024 | 2513900 | 31426607.0024 | 380709 | 98037 | 478746

## Scheme categories list
Category of scheme/measure
Bus priority infrastructure
Bus stops/stations/interchanges
Other infrastructure
Vehicles
Ticketing equipment/systems
Bus service support/network development
Simpler/more affordable fares
Safety and security
Improved information, marketing
Development of future proposals
LTA delivery/admin costs
Other