## Spend Overview
Highway Maintenance and ITB Scheme List 26/27
Funding
Financial Year | Highway Maintenance Block - Baseline | Highway Maintenance Block - Incentive | Local Transport Grant | Active Travel Capability Fund | Total
2026/27 | 5427000 | 1974000 | 1091000 | 271641 | 8763641
2027/28 | 6051000 | 2578000 | 2405000 | 271641 | 11305641
2028/29 | 6727000 | 2592000 | 3295000 | 271641 | 12885641
2029/30 | 8017000 | 2636000 | 4186000 | 271641 | 15110641
Total | 26222000 | 9780000 | 10977000 | 1086564 | 48065564
Highways Maintenance
| Works Type |  | Rephased budget from 2025/26 | 26/27 Funding | Total
| Resurfacing |  |  | 3122857.94 | 3122857.94
| Surface Dressing |  |  | 950947.94 | 950947.94
| Carriageway Patching |  |  | 991682.64 | 991682.64
| Drainage | Advanced Work Planning |  | 114400 | 114400
|  | Capital Drainage Allocation |  | 587440 | 587440
| Structures |  |  | 830725 | 830725
| Street Lighting |  |  | 115000 | 115000
| Footway Resurfacing |  |  | 95436.49 | 95436.49
| Reactive Patching |  |  | 392000 | 392000
| Advanced Work Planning |  |  | 70909.99 | 70909.99
| Specialist surveys |  |  | 129600 | 129600
| Rephased budget from 2025/26 |  | 2287036
|  |  | 2287036 | 7401000 | 9688036
Integrated Transport
|  | S106 | External Funding | Active Travel Fund | Rephased budget from 2025/26 | 26/27 Funding | Total
| Stage 5 | 63250 | 30000 | 80000 |  | 109096 | 282346
| Stage 6 |  |  | 191641 |  | 981904 | 1173545
| Rephased budget from 2025/26 |  |  |  | 917696
|  | 63250 | 30000 | 271641 | 917696 | 1091000 | 2373587

## Resurfacing Schemes
OVERVIEW
Ref | Class | Road No | Location | Parish | Digital Length | Str Indicator | Rcr Ranking | Comments | AM Treatment Type | Resurfacing Area (m2) | Priority | Confidence | Route to Market | Cost | Design Fees (4%) | Supervision Fees (4.9%) | Total Scheme Budget | Cored?
32232 | Unclassified | U0091 | CHESTNUT ROAD | LONG ASHTON | 185.62 | 65.59 | 720.1 | Considered in 24/25 | Resurfacing | 1193 | 1 | Medium | Wainwright | 59650 | 2386 | 3039.764 | 65075.764 | Yes
34553 | Unclassified | U0230 | BAILDON ROAD | WSM | 185.22 | 76.67 | 695.88 | Resurface. Close to Winterstoke Road | Reconstruction or geogrid | 1166 | 1 | Low | Wainwright | 75790 | 3031.6 | 3862.2584 | 82683.8584 | Yes
34372 | Unclassified | U0224 | CHURCHILL ROAD | WSM | 129.48 | 74.49 | 688.1 | Resurface, include Langford Road up to joint with newer material | Resurfacing | 1252 | 1 | High | Wainwright | 106420 | 4256.8 | 5423.1632 | 116099.9632 | Yes
34554 | Unclassified | U0230 | GRASMERE DRIVE | WSM | 259.47 | 76.91 | 620.42 | Do with Baildon | Reconstruction or geogrid | 1877 | 1 | Low | Wainwright | 122005 | 4880.2 | 6217.3748 | 133102.5748 | Yes
34631 | Unclassified | U0377 | LOWER QUEENS ROAD | CLEVEDON | 100.6 | 73.61 | 618.89 | Footways, kerbs, resurface PRIORITY. FWs 471m2 Kerbs 215m | Resurfacing, Footways, Channels, Kerbs, Associated Drainage | 907 | 1 | Low | Wainwright | 108840 | 4353.6 | 5546.4864 | 118740.0864 | Yes
34555 | Unclassified | U0230 | WINDERMERE AVENUE | WSM | 197.36 | 78.31 | 610 | Do with Baildon. Could ADD 404m2 FWs | Reconstruction or geogrid | 905 | 1 | Low | Wainwright | 58825 | 2353 | 2997.722 | 64175.722 | Yes
34646 | Unclassified | U0347 | MOORFIELD ROAD / WESTFIELD ROAD | BACKWELL | 472.04 | 59.54 | 604.44 | Resurface. AO reccomendation. FW outside 53 to be included LINK - ITB liveable neighbourhood scheme proposed here | Resurfacing | 3198 | 1 | High | Wainwright | 271830 | 10873.2 | 13852.4568 | 296555.6568 | No
32298 | Unclassified | U0095 | BIRDWELL ROAD | LONG ASHTON | 162.33 | 73.41 | 586.38 | Structural Resurfacing | Resurfacing | 797 | 1 | Low | Wainwright | 39850 | 1594 | 2030.756 | 43474.756 | Yes
34671 | Unclassified | U0230 | BAILDON CRESCENT | WSM | 284.33 | 75.66 | 352.83 | LINK - BAILDON ROAD | Reconstruction or geogrid | 2138 | 1 | Low | Wainwright | 138970 | 5558.8 | 7081.9112 | 151610.7112 | Yes
28289 | A Class | A370 | STATION ROAD, CONGRESBURY | CONGRESBURY | 445.31 | 81.51 | 304.01 | LINK - Wales & West Utilities gas works | Resurfacing | 7096 | 1 | High | Wainwright | 354800 | 14192 | 18080.608 | 387072.608 | Yes
34594 | Unclassified | U0220 | EARLHAM GROVE | WSM | 392.72 | 36.31 | 238.93 | See core report from 2017. Recon may be necessary due to low CBR and inconsistent capping layer. Costs based on £85/m2 Phase 1 Locking Rd to Birchwood Ave £254k Phase 2 Birchwood Ave to Ashcombe Rd £304k ITB liveable neighbourhood proposed | Reconstruction or geogrid £90m-2 | 2300 | 1 | Low | Wainwright | 322000 | 12880 | 16409.12 | 351289.12 | No
34677 | C Class | C738 B3130 To B3128 Long Ashton | LAMPTON ROAD | LONG ASHTON | 350.79 | 73.17 | 109.69 | Carriageway Resurfacing | Resurfacing | 620 | 1 | High | Wainwright | 27900 | 1116 | 1421.784 | 30437.784 | No
N/A | Unclassified | N/A | LONGRIDGE WAY ROUNDABOUT | WSM |  |  |  | Failed block paving in Weston Village | Resurfacing | N/A | 1 | Low | Wainwright | 100000 | 4000 | 5096 | 109096 | N/A
[14 empty] | 1786880 | 71475.2 | 91059.4048 | 1949414.6048
Ref |  | Road No | Location | Parish | Digital Length | Str Indicator | Rcr Ranking | Comments | AM Treatment Type | Resurfacing Area (m2) | Priority | Confidence | Route to Market | Rephased budget from 2025/26 | Difference | Required Budget | Supervision Fees (4.9%) | Total | Actual rephasing | Variance
32200 | A Class | A370 | WEST TOWN ROAD HILLSIDE TO RODNEY ROAD | BACKWELL | 920 |  |  | Scheme Deferred from 25/26 programme, additional budget required | Resurfacing | 6840 | 1 | High | Wainwright | 104000 | 231803.56 | 335803.56 | 11358.3744 | 243161.9344 | 102327.21 | -1672.79 | KDH201 PR2508
34508 | Unclassified | U0205 | ELLESMERE ROAD | UPHILL | 185 |  |  | Scheme Deferred from 25/26 programme, additional budget required | Resurfacing | 1184 | 1 | High | Wainwright | 58653 | 79000 | 137653 | 3871 | 82871 | 58653 | 0 | KDH302 UC2509
34591 | Unclassified | U004 | MILTON ROAD | WSM | 550 |  |  | Scheme Deferred from 25/26 programme, additional budget required | Resurfacing, Associated Drainage | 4970 | 1 | High | Wainwright | 220283 | 29717 | 250000 | 1456.133 | 31173.133 | 220283 | 0 | KDH302 UC2510
32240 | Unclassified | U0422 | YANLEIGH CLOSE | DUNDRY | 130 |  |  | Scheme Deferred from 25/26 programme, additional budget required | Resurfacing, Associated Drainage | 687 | 1 | High | Wainwright | 71502 | 48000 | 119502 | 2352 | 50352 | 71502 | 2732.45 | KDH302 UC2511
34652 | B Class | B3130 | TICKENHAM ROAD | CLEVEDON | 1280 |  |  | Scheme Deferred from 25/26 programme, additional budget required | Resurfacing | 14467 | 1 | High | Wainwright |  | 360098 | 360098 | 17644.802 | 377742.802 | 0 | 0
28267 | A Class | A370 | WESTON ROAD |  |  |  |  | Scheme Deferred from 25/26 programme, additional budget required | Resurfacing | 5640 | 1 | High | Wainwright | 36642 | 88593 | 125235 | 4341.057 | 92934.057 | 33014.5 | -3627.5 | KDH201 PR2504
32272 | Unclassified | U0236 | MONTPELLIER |  |  |  |  | Scheme Deferred from 25/26 programme, additional budget required | Resurfacing | 4236 | 1 | High | Wainwright | 146581.89 | 281418.88 | 428000.77 | 13789.5251 | 295208.4051 |  | -2567.84
[14 empty] | 637661.89 | 1118630.44 | 1756292.33 | 54812.8916 | 1173443.3316
RESERVE SCHEMES
Ref |  | Road No | Location | Parish | Digital Length | Str Indicator | Rcr Ranking | Comments | AM Treatment Type | Resurfacing Area (m2) | Priority | Confidence | Route to Market | Cost |  |  |  |  | Missing Schemes
32274 | Unclassified | U0339 | SOUTHFIELD ROAD | NAILSEA | 906.42 | 59.52 | 389.74 | Alligator cracking, lots and lots of prior patching. Breaking out in places | Resurfacing | 5146 | 1 | Low | Wainwright | 437410 |  |  |  |  | 37745 | Dundry Lane, Dundry | KDH202 NP2504
32292 | Unclassified | U0255 | GREENWOOD ROAD | WORLE | 185.67 | 80.48 | 682.65 | Resurface + 690m2 FWs | Resurfacing | 1264 | 1 | High | Wainwright | 56880 |  |  |  |  | 11503 | Woodborough Road, Winscombe | KDH208 DS2507
34557 | Unclassified | U0382 | THE AVENUE | CLEVEDON | 789.44 | 65.25 | 568.73 | Lots of failed jet patching. Multiple sunken trenches. Possibility to add 1717m2 of FWs | Resurfacing | 4671 | 1 | Low | Wainwright | 256905 |  |  |  |  | 146581.88 | Trewartha Park, Hill Road & Montpelier, W-s-M | KDH302 UC2514
32195 | Unclassified | Unc12 Avon Way, Portishead | AVON WAY | PORTISHEAD | 885.71 | 59.53 | 538.12 | Structural. Rutting, cracking and mud pumping through the cracks. May need 2 course surfacing if not more. Consider FWs. Costs based on £85/m2 £735k | Reconstruction or geogrid £90m-2 | 8558 | 1 | Low | Wainwright | 513480 |  |  |  |  | 79111.17 | B3133 BRINSEA ROAD and STOCK LANE - Venus Street to RBT Langford Lane | KDH208 DS2513
32229 | Unclassified | U0370 | HILL MOOR | CLEVEDON | 178.15 | 63.19 | 480 | Main drag of Hill Moor/ Moor Park cracked and delaminated. Resurface but maybe leave other bits for micro? Has been deferred a few times | Resurfacing | 480 | 1 | High | Wainwright | 21600
32230 | Unclassified | U0370 | MOOR PARK | CLEVEDON | 181.2 | 69.76 | 474.5 | See Hill Moor | Resurfacing | 473 | 1 | High | Wainwright | 21285
34405 | A Class | A369 | DENNY VIEW RD TO SANDY LANE | ABBOTS LEIGH | 1463.71 | 75.96 | 220.08 | Too far gone for SD and deteriorating fast. Inlay ITB scheme on junction with PILL ROAD CHECK EXTENTS snip saved in 26-27 folder | Resurfacing | 15271 | 1 | Medium | Wainwright | 534485
34504 | C Class | C405 Myrtle House.Fm. To Kenn | DOWNSIDE ROAD | BACKWELL | 1609.46 | 53.26 | 114.53 | Previously a recycling job. Heavy subsidence | Reconstruction or geogrid | 13300 | 1 | Low | Wainwright | 798000
2640045

## Surface Dressing Schemes
OVERVIEW
Ref | Class | Road No | Location | Parish | Digital Length | Str Indicator | Rcr Ranking | Comments | AM Treatment Type | SD Area (m2) | Priority | Confidence | Route to Market | Cost | Design Fees (4%) | Supervision Fees (4.9%) | Total Scheme Budget
34612 | Unclassified | U0414 | DIAL LANE | FELTON | 962.46 | 65.44 | 460.22 | Patched 25/26, surface dress | Surface Dressing | 4259 | 1 | High | Eurovia | 25554 | 1022.16 | 1302.2318 | 27878.3918
29529 | C Class | C499 | WINT HILL | BANWELL | 882.55 | 68.31 | 409.75 | Should be OK for Surface Dressing with only minor patching Patched 24/25 | Surface Dressing | 2830 | 1 | High | Eurovia | 16980 | 679.2 | 865.3008 | 18524.5008
34514 | A Class | A368 | THE COOMBE, BLAGDON | BLAGDON | 1570.8 | 65.56 | 393.38 | Pre patched 25/26 | Surface Dressing | 15210 | 1 | Low | Eurovia | 91260 | 3650.4 | 4650.6096 | 99561.0096
29650 | C Class | C405 | CHELVEY ROAD | NAILSEA | 2020 | 56.71 | 374.2 | Pre patched 25/26. Could be extended to 16471.3m2) | Surface Dressing, Associated Drainage | 9194 | 1 | High | Eurovia | 55164 | 2206.56 | 2811.1574 | 60181.7174
32172 | C Class | C43 | LONGWOOD AND WEIR LANE | LONG ASHTON | 768.91 | 78.4 | 337.82 | Pre patched 24/25 | Surface Dressing | 6156 | 1 | High | Eurovia | 36936 | 1477.44 | 1882.2586 | 40295.6986
32169 | C Class | C405 | BROCKLEY LANE | BACKWELL | 276.22 | 72.37 | 216.84 | Pre patched 25/26 | Surface Dressing | 7946 | 1 | High | Eurovia | 47676 | 1907.04 | 2429.569 | 52012.609
34665 | C Class | C434 | HIGH ST,PORTBURY | PORTBURY | 1020.56 | 46.49 | 178.53 | Pre surface dressing patched | Surface Dressing | 3516 | 1 | High | Eurovia | 21096 | 843.84 | 1075.0522 | 23014.8922
34711 | Unclassified | U0396 | ASHEY LANE | WRINGTON | 1437.83 | 48.04 | 285.5 | Surface dressed ~7 years ago, some minor patching done, maybe too much to do for in year patching? | Surface Dressing | 9962 | 1 | Low | Eurovia | 119544 | 4781.76 | 6091.9622 | 130417.7222
34708 | B Class | B3124 | CLEVEDON RD | WALTON IN GORDANO | 6193.34 | 68.42 | 191.2 | Surface dressed ~7 years ago, minimal in year patching required at WiG | Surface Dressing | 37255 | 1 | Medium | Eurovia | 335295 | 13411.8 | 17086.6332 | 365793.4332
29651 | C Class | C405 | NAILSEA WALL LANE | NAILSEA | 450 | 65.51 | 401.94 | Patching taking place 25/26 so SD 26/27. Could be extended to cover newer section patched section adjacent to Nailsea Wall Farm (new scheme area 4417.2m2) | Surface Dressing, Associated Drainage | 1528 | 1 | High | Eurovia | 17264.6 | 690.584 | 879.804 | 18834.988
29533 | C Class | C499 | WHITLEY ROAD | BANWELL | 634 | 67.67 | 300.53 | Pre patched 24/25 | Surface Dressing | 2628 | 2 | High | Eurovia | 15768 | 630.72 | 803.5373 | 17202.2573
34470 | C Class | C422 | WALTON STREET | WALTON IN GORDANO | 2880 | 75.1 | 255.85 | Pre patched 25/26 | Surface Dressing | 14854 | 3 | High | Eurovia | 89124 | 3564.96 | 4541.759 | 97230.719
[14 empty] | 871661.6 | 34866.464 | 44419.8751 | 950947.9391
RESERVE SCHEMES
Ref | Class | Road No | Location | Parish | Digital Length | Str Indicator | Rcr Ranking | Comments | AM Treatment Type | SD Area (m2) | Priority | Confidence | Route to Market | Cost
29094 | B Class | B3128 | CLARKEN COOMBE | LONG ASHTON | 1811.53 | 83.17 | 176.9 | Patched 25/26, surface dress. SD extents extended to the Festival Way crossing. DEFER TO YR2 | Surface Dressing | 22853 | 1 | Medium | Eurovia | 205677
34602 | Unclassified | U0395 | LANGFORD LANE | LANGFORD | 734 | 65.23 | 600.1 | Looks scruffy but perfect candidate to use a surface dressing to arrest deterioration. Minimal in year patching on worst bits | Surface Dressing | 7560 | 1 | Low | Eurovia | 90720
29874 | C Class | C439 | YANLEY LANE, LONG ASHTON | LONG ASHTON | 903.6 | 58.11 | 286.13 | Almost all fine for SD with minor patching, check hardness. BUT area near the brook has been wet so will need patching. Measure includes Glebe Road | Surface Dressing | 15432 | 1 | Low | Eurovia | 185184
34599 | Unclassified | U0399 | LADYMEAD LANE / JUBILEE LANE / PUDDING PIE LANE | LANGFORD | 796 | 60.65 | 538.42 | Good to go | Surface Dressing | 13944 | 1 | High | Eurovia | 83664
34644 | C Class | C440 | CLAVERHAM ROAD, YATTON | YATTON | 1833.12 | 79.38 | 121.95 | Patched recently, SD. Some pre patching required. NEEDS DOING | Surface Dressing | 9711 | 1 | Low | Eurovia | 116532
681777

## Patching Schemes
OVERVIEW
Ref | Class | Road No | Location | Parish | Digital Length | Str Indicator | Rcr Ranking | Comments | AM Treatment Type | Pre Patching Area | Priority | Confidence | Route to Market | Cost | Design Fees (4%) | Supervison Fees (4.9%) | Total Scheme Budget
32265 | Unclassified | U0235 | CECIL ROAD | WSM | 519.08 | 57.43 | 578.86 | Pre surface dressing patching | Pre Patching | 7322 | 1 | Low | Wainwright | 80542 | 3221.68 | 4104.4203 | 87868.1003
29959 | C Class | C444 | BEACH ROAD, KEWSTOKE | KEWSTOKE | 47.67 | 58.35 | 280.63 | Patch then surface dress the entire length. Inc footway from Rocksalt restaurant to Crookes Lane. Lots of patching may be too far gone | Pre Patching | 17710 | 1 | Low | Wainwright | 150000 | 6000 | 7644 | 163644
34483 | C Class | C404 | BARTON ROAD, WINSCOMBE | WINSCOMBE | 2907.56 | 82.1 | 287.81 | Hardness test before a SD. LOTS of skid marks here. PRE PATCH YR1 DRESS YR2 ALONGSIDE MAX MILL ROAD | Pre Patching, Associated Drainage | 20194 | 1 | Low | Wainwright | 222134 | 8885.36 | 11319.9486 | 242339.3086
34545 | C Class | C499 | MAX MILL LANE | WINSCOMBE | 1447.32 | 78.11 | 483.71 | Patching done here recently "B:\D&E\Highways & Transport\Street Scene\Highways Works\2024-25\603 - Banwell\PA - Patching\PA02 - Max Mill Lane\24-603-PA02 - Max Mill Lane" PRE PATCH YR1 DRESS YR2 ALONGSIDE BARTON RD | Pre Patching, Associated Drainage | 6970 | 1 | Low | Wainwright | 76670 | 3066.8 | 3907.1032 | 83643.9032
32167 | C Class | C405 | WEST LANE, FELTON | FELTON | 730.12 | 85.25 | 160.25 | Was SD, deferred for 8/9 years, now in need of fairly extensive patching. HRA so would be good to extend the life by Surface dressing after patching. Cut short at A38 to tie in with MRN resurfacing extents and extend E to Felton Lane | Pre Patching | 15555 | 1 | Low | Wainwright | 171105 | 6844.2 | 8719.5108 | 186668.7108
34710 | Unclassified | U0351 | CHESTON COOMBE | BACKWELL | 1569.01 | 59.31 | 402.61 | Previously SD'd. Some patches of red | Patching | 8362 | 1 | Low | Wainwright | 91982 | 3679.28 | 4687.4027 | 100348.6827
34516 | Unclassified | U0122 | PURN WAY | BLEADON | 452.18 | 71.45 | 381.36 | Section adjacent to croquet club worst - revenue patch? Looks like vehicles run onto verge | Patching | 2401 | 2 | Low | Wainwright | 26411 | 1056.44 | 1345.9046 | 28813.3446
32278 | Unclassified | U0410 | BROOKSIDE | WINFORD | 136.7 | 61.89 | 775.63 | some surface stripping and possibly cracking/crazing localised to ironworks? | Patching | 646 | 3 | Low | Wainwright | 7106 | 284.24 | 362.1218 | 7752.3618
31176 | Unclassified | U0308 | LOCKING HEAD DROVE | LOCKING | 239.36 | 63.7 | 726.31 | Short section with just farm/business traffic, some structural defects and edge deterioration. Overlay or patch | Patching | 858 | 3 | Low | Wainwright | 9438 | 377.52 | 480.9605 | 10296.4805
31158 | Unclassified | U0306 | MOOR ROAD | BANWELL | 774.74 | 68.36 | 701.92 | Quiet lane, crosses route of Banwell Bypass. Could do with patching and possibly dressing. Some edge deterioration. | Patching | 6692 | 3 | Low | Wainwright | 73612 | 2944.48 | 3751.2675 | 80307.7475
[14 empty] | 909000 | 36360 | 46322.64 | 991682.64 | 46322.64

## Drainage
OVERVIEW
Class | Location | Parish | Digital Length | Str Indicator | Rcr Ranking | Comments | AM Treatment Type | Cost | Design Fees (4%) | Supervision Fees (4.9%) | Total Scheme Budget | Budget
A Class | STATION CLOSE TO CONGRESBURY BRIDGE | CONGRESBURY | 445.31 | 81.51 | 304.01 | Surface water ponding through out. Survey from Moor Bridge ditch to Congresbury traffic lights to outfall. Survey (Jet, CCTV, GPR & Topo) works to inform design. Survey £30k from advanced works planning budget. | Resurfacing | 30000 | 1200 |  | 31200 | Advanced works planning budget
Unclassified | AVON WAY | PORTISHEAD | 885.71 | 59.53 | 538.12 | Surface water coming up through road. Cause unkown. Ground water or drainage flows from highway system, Wsx system & section of culvert present. Jet and survey entire extents of highway drainage system and culvert. Request Wsx Survey their system. Survey £30k from advanced works planning budget. | Reconstruction or geogrid £90m-2 | 30000 | 1200 |  | 31200 | Advanced works planning budget
C Class | WEST LANE, FELTON | FELTON | 730.12 | 85.25 | 160.25 | Surface water ponding. CCTV survey entire extents to inform design. Survey £15k from advanced works planning budget. | Pre Patching | 15000 | 600 |  | 15600 | Advanced works planning budget
C Class | CLAVERHAM ROAD, YATTON | YATTON |  |  |  | Reports of flooding properties 49, 139 & 141. Survey £15k. Works £40k. Paid by capital drainage allocation. |  | 15000 | 600 |  | 15600 | Advanced works planning budget
Unclassified | LADYMEAD LANE / JUBILEE LANE / PUDDING PIE LANE | LANGFORD |  |  |  | Surface water ponding through out. Survey (CCTV) entire extents to inform design. Survey £20k from advanced works planning budget. | Surface Dressing | 20000 | 800 |  | 20800 | Advanced works planning budget
[8 empty] | 110000 | 4400 | 0 | 114400
Class | Location | Parish | Digital Length | Str Indicator | Rcr Ranking | Comments | AM Treatment Type | Cost | Design Fees (4%) | Supervision Fees (4.9%) | Total Scheme Budget | Budget
A Class | STATION CLOSE TO CONGRESBURY BRIDGE | CONGRESBURY | 445.31 | 81.51 | 304.01 | Survey to inform works, paid by capital drainage allocation. Estimated cost £80k | Resurfacing | 80000 | 3200 | 4076.8 | 87276.8 | Capital drainage allocation
Unclassified | AVON WAY | PORTISHEAD | 885.71 | 59.53 | 538.12 | Survey to inform works, paid by capital drainage allocation. Estimated cost £50k | Reconstruction or geogrid £90m-2 | 50000 | 2000 | 2548 | 54548 | Capital drainage allocation
C Class | WEST LANE, FELTON | FELTON | 730.12 | 85.25 | 160.25 | Survey to inform works, paid by capital drainage allocation. Estimated cost £30k |  | 30000 | 1200 | 1528.8 | 32728.8 | Capital drainage allocation
Unclassified | PURN WAY | BLEADON | 452.18 | 71.45 | 381.36 | Jet entire extents to inform dig down repairs. Survey: £10k. Works: £15k. Paid by capital drainage allocation. | Patching | 25000 | 1000 | 1274 | 27274 | Capital drainage allocation
C Class | WALTON STREET / DOWN RD | PORTISHEAD | 689.65 | 75.1 | 255.85 | CCTV survey here. Jetting, CCTV and dig down crew. Estimated cost £40k. Paid by capital drainage allocation. | Surface Dressing | 40000 | 1600 | 2038.4 | 43638.4 | Capital drainage allocation
C Class | CLAVERHAM ROAD, YATTON | YATTON | 1833.12 | 79.38 | 121.95 | Survey to inform works, paid by capital drainage allocation. Estimated cost £30k | Surface Dressing | 40000 | 1600 | 2038.4 | 43638.4 | Capital drainage allocation
Unclassified | LADYMEAD LANE / JUBILEE LANE / PUDDING PIE LANE | LANGFORD |  |  |  | Survey to inform works, paid by capital drainage allocation. Estimated cost £80k | Surface Dressing | 70000 | 2800 | 3567.2 | 76367.2 | Capital drainage allocation
Unclassified | Wrington Lane | Congresbury |  |  |  | 50% obstruction/collapse within culvert, frequently blocked, resulting in property flooding. Repair culvert to increase surface water flows. |  | 30000 | 1200 | 1528.8 | 32728.8 | Capital drainage allocation
A Class | Woodborough Road | Winscombe |  |  |  | Water surcharging through carriageway, cause unknown. Exploratory works and introduction of passive filtration. |  | 40000 | 1600 | 2038.4 | 43638.4 | Capital drainage allocation
A Class | Main Road | Cleeve |  |  |  | No highway drainage outfall or historical records to confirm. Investigation works to confirm outlet/outfall. Works on private land to install highway drainage outfall. Budget rephased from 25/26 FY. |  | 50000 | 2000 | 2548 | 54548 | Capital drainage allocation
C Class | Wolvershill Road | Banwell |  |  |  | Surface water flooding and multiple utility intrusions. Survey complete. Joint scheme with flood risk as HW system discharges into pond and resident discharges onto HW. |  | 13461.54 | 538.4616 | 686.0001 | 14686.0017 | Capital drainage allocation
C Class | Langford Road | Langford |  |  |  | Blocked culverts and in-filled ditches from A38 to brook resulting in property flooding. Reform ditches and clear culverts. |  | 25000 | 1000 | 1274 | 27274 | Capital drainage allocation
C Class | Wild Country Lane | Long Ashton |  |  |  | Surface water flooding at railway bridge, preventing passage. Jet entire highway drainage system and replace off-set gullies to catch surface water flows. |  | 40000 | 1600 | 2038.4 | 43638.4 | Capital drainage allocation
B Class | North End Road & High Street | Yatton |  |  |  | Surface water ponding throughout. Extent of works and cause unknown. Investigation works to confirm design in later FY. |  | 40000 | 1600 | 2038.4 | 43638.4 | Capital drainage allocation
Unclassified | Station Road | St Georges |  |  |  | Surface water flooding due to historical outfall currently obstructed and unknown. Unable to CCTV. Investigation works to prove/locate outfall. Alternative outfall potentially available. Liaise with design team. |  | 15000 | 600 | 764.4 | 16364.4 | Capital drainage allocation
[8 empty] | 588461.54 | 23538.4616 | 29988.0001 | 641988.0017
[10 empty] | 27440.0001 | 587440.0017

## Structures
OVERVIEW
| Plan / Scheme Reference | Team Leader / Officer | Type of Scheme | Justification | Proposed Delivery | Works Description & Issues | Cost Centre | Scheme costs based on new rates | Delivery timeframe | Confidence | Route to Market | Client Fees (4.9%) | Design Fees (20%) | Total | Spreadsheet formatting order (puts the spreadsheet back to its original formatting order)
Weston Road Retaining wall South (Phase 2) | 56W016 | Chandan Bhumpelly | Maintenance - Structure | In year allocation | 2026-27 | Delaminated Retaining wall Repairs and Rebuilding works | KDH203 | 250000 | 2026-2027 | High | DPS | 12250 | 50000 | 312250
Damson Road Footbridge (Over the Railway) | 36001 | Chandan Bhumpelly | Maintenance - Structure | In year allocation | 2026-27 | Bridge Deck Drainage installation | KDH203 | 100000 | 2026-2027 | Medium | DPS | 4900 | 20000 | 124900
Lower Strode Bridge | 56112 | Chandan Bhumpelly | Maintenance - Structure | In year allocation | 2026-27 | Silt Removal, Scour Repairs and Masonry Arch Repairs | KDH203 | 100000 | 2026-2027 | Medium | DPS | 4900 | 20000 | 124900
Urchinwood | 46061 | Chandan Bhumpelly | Maintenance - Structure | In year allocation | 2026-27 | Masonry Arch Repairs | KDH203 | 50000 | 2026-2027 | Medium | DPS | 2450 | 10000 | 62450
Suymmerways Railway Culvert | 35048 | Chandan Bhumpelly | Maintenance - Structure | In year allocation | 2026-27 | Culvert Parapet, Headwalls and Invert levels Repairs | KDH203 | 25000 | 2026-2027 | High | DPS | 1225 | 5000 | 31225
Structural Assessment Investigations |  | Chandan Bhumpelly | Maintenance - Structures | Necessary function of the Bridges & Structures work area | 2026/27 | n/a | KDH203 | 75000 | 2026-27 | High |  |  |  | 75000
Principal Inspection |  | Chandan Bhumpelly | Maintenance - Structures | Necessary function of the Bridges & Structures work area | 2026/27 | n/a | KDH203 | 100000 | 2026-27 | High |  |  |  | 100000
Road Restraint Maintenance rolling programme |  | Chandan Bhumpelly | Maintenance - Structures | Statutory Highway Function. | 2026/27 | Alternative funding source | KDH214 | 100000 | 2026-27 | High |  |  |  | 100000
Money set aside for Highways Structures post Flooding |  | Chandan Bhumpelly | Maintenance - Structures |  | 2026/27 | n/a | KDH203 | [6 empty] | 0
[12 empty] | 25725 | 105000 | 830725
25725
Note on H2: Lindsay Margerison: If code in grey, this is a code from a previous financial year and will need updating

## Street Lighting
OVERVIEW
Scheme Description | Plan / Scheme Reference | Team Leader / Officer | Type of Scheme | Justification | Proposed Delivery | Works Description & Issues | Cost Centre | Scheme costs based on new rates | Delivery timeframe | Confidence | Route to Market | Scheme Costs 2025-26 | Rephased Client Fees 2025-26 | Rephased Design Fees 2025-26 | Total Rephased From 2025-26 | Client Fees (4.9%) | Design Fees (20%) | New Allocation Total | Grand Total | Actual rephasing | Variance
ATF4 Pedestrian Wait Times | n/a | Mark Cogan (Jon Gall) / Adam Clarke | Improvement | Dft Funded Bid | 2026-27 | Improved detection for busy crossings to extend crossing times during heavy pedestrian demand | ?? |  | 2026-27 | High | Centregreat | 20888.711 | 1023.5468 | 4177.7422 | 26090 | 0 | 0 | 0 | 26090 | 0 | -26090 | DUPLICATE, THIS HAS BEEN INCLUDED ON ITB STAGE 6
Traffic Signal Maintenance Improvements | n/a | Mark Cogan / Adam Clarke | Maintenance | Rephased funding (potentially more available) | 2026-27 | Ageing Poles, an Alternative solution to failed traffic loops | KDH205 TS2601 |  | 2026-27 | Medium | Centregreat | 18248.1986 | 894.1617 | 3649.6397 | 22792 | 9 | 0 | 0 | 22801 | 23717 | 925 | KDH205 TS2501 & KDH205 TS2502
Private Cable Network | n/a | Mark Cogan / Gary Clare | Maintenance | Ageing cable network | 2026-27 | Review and Prioritise Private Cable Network maintenance improvements. | KDH204 SL2601 |  | 2026-27 | Medium/High | Centregreat | 52041.6333 | 2550.04 | 10408.3267 | 65000 | + | 0 | 0 | 65000 | 65000 | 0 | KDH204 SL2501
Pole Bracket Replacements | n/a | Mark Cogan / Gary Clare | Maintenance | Life expired Pole Brackets | 2026-27 | 76t | KDH204 SL2602 |  | 2026-27 | High | Centregreat | 32025.6205 | 1569.2554 | 6405.1241 | 40000 | 0 | 0 | 0 | 40000 | 40000 | 0 | KDH204 SL2501
Column Replacements | n/a | Mark Cogan / Gary Clare | Maintenance | Structurally failed lighting columns | 2026-27 | Design/Replace structurally failed lighting columns and design/programme 2027028 lighting columns | KDH204 SL2603 | 44035.2282 | 2026-27 | High | Centregreat | 20016.0128 | 980.7846 | 4003.2026 | 25000 | 2157.7262 | 8807.0456 | 55000 | 80000 | 25000 | 0 | KDH204 SL2501
Deillumination of Signs and Bollards | n/a | Mark Cogan / Gary Clare | Maintenance Improvement | Replace to current standard. Energy/Maintenance reduction | 2026-27 | Review remaining assets, produce a priority list and deliver replacements | KDH205 SL2604 | 48029.4307 | 2026-27 | High | Centregreat |  | 0 | 0 | 0 | 2353.8831 | 9607.6861 | 59991 | 59991 |  | 0
[12 empty] | 143220.1761 | 7017.7886 | 28644.0352 | 178882 | 4520.6093 | 18414.7318 | 114991 | 293882 |  | -25165

## ITB Stage 5
OVERVIEW
Scheme reference | Scheme title | Project description | Ward(s) | Parish(es) | Contract | Cost centre | Cost code(s) | Project code | Profess code | S106 Funding | External funding | ATF | 25/26 Slip | 26/27 ITB | Supervision Fees (4.9%) | TOTAL FUNDING | Actual rephasing | Variance
IT0461 | Perrings (Nailsea Active Travel_SW Circular) - Design and consultation only | St Marys Grove to the Perrings (£265,086), The Perrings to Backwell Lake (£53,127), Youngwood Lane to Station Close (£2,300), Additional Cycle Parking at Backwell Station (£6900) Planning Ref 16/P/1677/OT2 NEEDS TO BE SPLIT INTO SEPARATE PROJECTS | Multiple | Nailsea | DPS | Urban Active Travel |  |  | IT0461 | 49000 |  |  | 4866.01 |  |  | 53866.01 | 4866.01 | 0 | KDH104 EC2505
IT0861 | Youngwood Lane, Nailsea - off-site highway - North Road, Hanham Way, Queens Road | Towards capacity and highway safety improvements to North Street / Hanham Way / Queens Road junction. 16/P/1677/OT2. Scheme to allow for the transition of Queens Road Segregated cycle route onto North Street (IT0329a) and North Road pedestrian Improvements (Scrutiny Scheme IT1396) | Nailsea Youngwood | Nailsea | DPS | Congestion management |  |  |  | 7500 | [5 empty] | 7500 | 0 | 0
IT0862 | Queens Road/ Station Road Junction | Towards capacity and highway safety improvements to junction. 16/P/1677/OT2. | Nailsea West End | Nailsea | TBA | Congestion management |  |  |  | 6750 | [5 empty] | 6750 | 0 | 0
IT0479 | Supporting Active Travel in Winscombe, Sandford and Churchill - Sandmead Road | Sandmead Road is a rat-run but is also used by pedestrians and cyclists attending Churchill Academy. Introduce a Modal Filter on Churchill Green and create a short section of greenway to overcome the issue of vehicular/ pedestrian conflict. Design work required on Hill Rd part of route between Winscombe & Sandford. | Banwell & Winscombe | Winscombe and Sandford |  | Access to school |  |  |  |  | 25000 |  |  |  |  | 25000 | 0 | 0
IT0480 | Supporting Active Travel in Winscombe, Sandford and Churchill - crossing facilities | Lack of crossing facilities along Hill Road/ South Croft to aid pedestrian movement from Winscombe to Sandford. Undertake a traffic count and gap assessment in line with Assessment of Walked Routes to School guidance. | Banwell & Winscombe | Winscombe and Sandford |  | Access to school |  |  |  |  | 5000 |  |  |  |  | 5000 | 0 | 0
IT0271b | Weston Station Active Travel Gateway / Francis Fox Rbt pedestrian and cycle crossing improvements and Station Rd cycle facilities LCWIP Weston Cycle Route 3/4 | Project to raise the parapet across Hildesheim Bridge to make the route accessible and safe for cycle use. | Weston-Super-Mare Central | Weston-Super-Mare | DPS | Rail/Access to rail |  |  | IT0271 |  |  | 50000 |  |  |  | 50000 | 0 | 0
IT0329a | LCWIP Cycle Route Nailsea 2: Queens Rd Segregated cycling route | Provide segregated path along north side of Queens Road between North St and Coombe Rd. Topographical Survey, Design, Costing, Consultation | Multiple | Nailsea | TBA | Urban Active Travel |  |  | IT0329 |  |  | 18000 |  |  |  | 18000 | 0 | 0
IT0329b | LCWIP Cycle Route Nailsea 2: Mizzymead Rd | Provide segregated path along Mizzymead Rd between Hillcrest Rd and High Street. Topographical Survey, Design, Costing, Consultation | Multiple | Nailsea | TBA | Urban Active Travel |  |  | IT0329 |  |  | 12000 |  |  |  | 12000 | 0 | 0
IT1478 | J21 - A370 Smallway Road Safety Route Review | 2021-23 Route Analysis identified multiple collisions along a 7Km route of the A370 between J21 and Smallway signalised junction at Congresbury. This project seeks to investigate and design road safety improvements along the route to reduce the reoccurrence and severity of similar collisions taking place. | Banwell & Winscombe / Congresbury & Puxton | Banwell / Puxton / Congresbury | NA | Road Safety |  |  | IT1478 |  |  |  | 10000 |  |  | 10000 | 0 | -10000
IT1005 | Earlham Grove Liveable Neighbourhood | Liveable neighbourhood project to build on upcoming adjacent Liveable Neighbourhood, further reducing through traffic to both areas, improvements for safe school travel to Ashcombe Primary. Potential to spread Liveable Neighbourhood between Ashcombe Rd and Chesham Road South. Scheme to include 20mph speed limit (previously to be delivered by Weston Central Residential 20 speed limit | Weston-Super-Mare Milton | Weston-Super-Mare | DPS | Liveable Neighbourhood |  |  | IT1005 |  |  |  | 15000 |  |  | 15000 | 18000 | 3000 | KDH106 ST2507
ITx002 | Road Safety - Investigation and design work for future years | Analysis of 2025 collision data to identify trends and bring forward proposals for future interventions | District Wide | District Wide | NA | Road Safety |  |  | H&T000282 |  |  |  | 0 | 10000 | 490 | 10000 | 0 | 0
IT0325 | The Causeway/ Hanham Way, Nailsea. Traffic reduction (Scrutiny schemes) | To introduce a reduction in the speed and volume of traffic using the route. Future funding may be available from S106 to introduce any agreed physical works. | Multiple | Multiple | TBA | Rural active travel |  |  | IT0325 |  |  |  | 0 | 10000 | 490 | 10000 | 0 | 0
TBA | iRAP Programme of collision reductions on Principal Highway Network | A370 Congresbuy to Backwell Safety Review and outline intervention design | Banwell & Winscombe / Congresbury & Puxton | Banwell / Puxton / Congresbury | NA | Road Safety |  |  | IT1478 |  |  |  |  | 30000 | 1470 | 30000 | 0 | 0
IT0270a | Weston Town Centre to Worle & Locking Castle (LCWIP Weston Cycle Routes 1 & 2) | Extending Milton Road cycle route into town. Options include using the Milton Road cycle or extend Baker St cycle route to provide a cycle contraflow on Meadow Street. Include what the traffic management proposals to reduce traffic and improve cycle permeability out of town | Multiple | Weston-Super-Mare |  | Urban Active Travel | [7 empty] | 6000 | 294 | 6000 | 0 | 0
IT0270b | Weston Town Centre to Worle & Locking Castle (LCWIP Weston Cycle Routes 1 & 2) | Review speed limit on Beaufighter Road and improvements to crossing point. Include declutter and vegetation clearance on path towards A370. Topographical Survey at junction, Design, costing, consultation | Multiple | Weston-Super-Mare |  | Urban Active Travel | [7 empty] | 8000 | 392 | 8000 | 0 | 0
IT1465 | Improve signing of Brean Down Way | Improve the signing of the BDW from Weston Grand Pier to authority boundary (River Axe). Encourage SCC to sign their section. Current signing is low key (some junctions only stickers) and only refers to NCN33, not the 'Brean Down Way' or destinations. This gives the route a low profile, yet it should be one of our flagship routes. | Multiple | Weston-super-Mare |  | Rural active travel | [7 empty] | 10000 | 490 | 10000 | 0 | 0
IT0263 | TROs for school keep clear markings - To be delivered in phases | Review and remarking of school keep clear markings with the objective of eventually having all school keep clears supported by a TRO and properly signed and lined so they may be enforced. Prioritise maintenance programme and easy wins with others to follow later | District Wide | District Wide | NSEC | Access to school |  |  | H&T000301 |  |  |  |  | 10000 | 490 | 10000 | 0 | 0
IT0232 | Weston Central Residents Parking Scheme (RPS) physical works | Review of Resident Parking Scheme in central Weston-super-Mare | Weston-super-Mare Central | Weston-super-Mare |  | Parking Management (>£5k) |  |  | H&T000315 |  |  |  |  | 20000 | 980 | 20000 | 0 | 0
TBA | LEVI site assessments | Engineer support for the role out of EV charging points across the district |  |  | NA | E-mobility |  |  |  |  | TBA | [5 empty] | 0 | 0
[10 empty] | 63250 | 30000 | 80000 | 29866.01 | 104000 | 5096 | 307116.01 |  | -7000
Note on K2: Hilary D Crouch: vlookup from finance tab
Note on L2: Hilary D Crouch: vlookup from finance tab
Note on N2: Hilary D Crouch: vlookup from finance tab
Note on O2: Hilary D Crouch: vlookup from finance tab
Note on Q2: Hilary D Crouch: vlookup from finance tab

## ITB Stage 6
OVERVIEW
Scheme reference | Scheme title | Project description | Ward(s) | Parish(es) | Contract | Cost centre | Cost code(s) | Project code | Profess code | ATF | 25/26 Slip | 26/27ITB Funding | Supervision Fees (4.9%) | TOTAL FUNDING |  | Actual rephasing | Variance
IT0271a | Hildesheim Bridge Puffin Crossing | To provide a new signalised crossing to improve pedestrian and cycle connectivity to Weston-super-Mare Railway Station |  |  | DPS | Rail/Access to rail |  |  |  | 165000 |  |  |  | 165000 |  | 0 | 0
IT0463 | ATF4: Signalised Crossings: Pedestrian Wait Times Reduction. Budget to be transferred to Signals Team (Mark Cogan) | Reduced pedestrian wait times at signalised crossings for pedestrians. Scheme substantially completed 2023/24 with remaining budget to be moved to Signals for further phase to be completed in 26/27. |  |  | NA | [5 empty] | 26090 |  |  | 26090 |  | 26090 | 0 | KDH105 RS2512
IT0225a | Upgrade of EATF1 works to permanent solutions - St. Johns, Clevedon | Adjust School Keep Clears around build-out and remove planters |  |  | TBA | Access to school |  |  |  |  | 10000 |  |  | 10000 |  | 0 | -10000 | KDH112 AT2501
IT0225b | Upgrade of EATF1 works to permanent solutions - Highdown, Portishead | Remove Planters, introduce junction narrowing on Tower Road, introduce footpath wher people walk over the mud on unction with The Downs |  |  |  | Access to school |  |  |  |  | 30000 |  |  | 30000 |  | 30000 | 0 | KDH112 AT2501
IT0225c | Upgrade of EATF1 works to permanent solutions - Worle Village, Worle | Make one-way permanent, remove planters, tighten Bellmouth of Hill Road, introduce parking restrictions (absorb into PRaMS) to keep footpath clear, trim or remove school hedge, adjust School Keep Clear TRO to reflect what is on site. |  |  |  | Access to school |  |  |  |  | 38000 |  |  | 38000 |  | 37916 | -84 | KDH112 AT2501
IT0515 | A371 Knightcott Road: Weston-super-Mare to Banwell Missing Link (LCWIP Weston-super-Mare Cycling Route 4) | The scheme fills a missing link in the strategic cycling network that will emerge between existing infrastructure to the west and committed infrastructure to the east on the A371 between Weston-super Mare and Banwell. Scheme to be delivered as part of Banwell by-pass implimentation. |  |  | DPS | Rural active travel |  |  |  |  | 305000 |  |  | 305000 |  | 300000 | -5000 | KDH104 EC2503
IT0331 | ATF5 - Festival Way (Golden Valley Bridleway) | - Improve existing narrow section of Festival Way (Golden Valley), and connections from - Trendlewood Way to Nailsea High Street |  |  | DPS | Urban Active Travel |  |  |  |  | 115072 |  |  | 115072 |  | 105000 | -10072 | KDH104 EC2506
IT1253 | Clevedon Seafront (Phase 2) | Provision of public realm improvements including planters, signage and seating | Clevedon Walton | Clevedon |  | Public realm | KDH304 |  | H&T000405 |  | 80000 |  |  | 80000 |  | 0 | -80000
IT1349 | Road Safety - Weston-super-Mare A370 Speed Limit improvements (Phase 1 and Phase 2 combined) | Review of speed limits on the main dual carriageway into Weston-super-Mare to make more consistent and reduce number and severity of accidents. Unfunded pending consultation. | Multiple | Weston-super-Mare | DPS/ NSEC | Speed reduction |  |  |  |  | 95000 | 80000 | 3920 | 178920 |  | 95000 | 0 | KDH105 RS2502
IT1468 | NSC Electric Vehicle Charging Infrastructure. Do not show scheme on ITB Monitor as being managed by STARS Team | Support funding for NSC EV Fleet chargers. |  |  |  | E-mobility |  |  |  |  | 50000 | 50000 | 2450 | 102450 | ? | 0 | -50000
IT1366 | Review Prohibition of Cycling Traffic Orders and barriers | Review all the traffic orders and barriers which prohibit cycling in North Somerset with a view to revoking those where we want to now encourage more cycling. |  |  | NSEC | Urban Active Travel |  |  |  |  | 5000 | 10000 | 490 | 15490 |  | 0 | -5000
ITXXX | Scrutiny Panel Choice Schemes | Scrutiny Priority Schemes - Budget to be proportioned between schemes and this line in the programme to be deleted | [8 empty] | 225000 | 150000 | 7350 | 382350 |  | 223724 | -1276 | KDH106 ST2503
IT1339 | Milton Park School Street | Improve pedestrian access to school | Weston-super-Mare Milton | Weston-super-Mare | DPS | Access to school |  |  | IT1339 |  | 6000 | 54000 | 2646 | 62646 |  | 0 | -6000
IT1568 | B3128 Slip Road from A370 / Access Road to Park & Ride | The slip road from the A370 long Ashton Bypass travelling towards the P&R site has experienced a number of colisions some of them head on with drivers travelling south west bound from the A370 crossing the double white centre lines and coliding with vehicles travelling in the opposite direction |  |  | NSEC | Road Safety | [5 empty] | 30000 | 1470 | 31470 |  | 0 | 0
ITx005 | Pedestrian drop kerbs | Introduction of pedestrian dropped kerbs in areas of high demand where there are currently none provided. Programme to include Crockern School and Salisbury Terrace. |  |  | NSEC | Liveable Neighbourhood | [5 empty] | 50000 | 2450 | 52450 |  | 0 | 0
IT0263 | TROs for school keep clear markings - To be delivered in phases | Review and remarking of school keep clear markings with the objective of eventually having all school keep clears supported by a TRO and properly signed and lined so they may be enforced. Prioritise maintenance programme and easy wins with others to follow later |  |  | NSEC | Access to school | [5 empty] | 30000 | 1470 | 31470 |  | 0 | 0
ITx004 | PRaMS | Parking Restrictions and Minor Schemes. |  |  | NSEC | PRaMS (< £5k) | [5 empty] | 100000 | 4900 | 104900 |  | 0 | 0
IT1294 | Birnbeck Road Madeira Road junction | No drop kerbs on main pedestrian route and road safety issue with 3 cyclists and 1 pedestrian injured over 5 year period. Propose to square up the junction and provide tactile crossing - refer to sketch on project folder. On pier to pier cycle route. |  |  | DPS or NSEC | Urban Active Travel | [5 empty] | 40000 | 1960 | 41960 |  | 0 | 0
IT0526 | Castlemead Pedestrian facilities | There are no dropped kerbs or tactile paviours at this junction. Scheme to be delivered in conjunction with maintenance scheme. |  |  | DPS/NSEC | Urban Active Travel | [5 empty] | 80000 | 3920 | 83920 |  | 0 | 0
| Cycleway maintenance | Previous revenue budget - decision made to capitalise. Managed by STARS Team - DO not show on ITB Monitor |  |  | NA | Maintenance issue | [5 empty] | 25000 | 1225 | 26225 |  | 0 | 0
IT0425 | Winford C of E Primary School Pedestrian Improvements. | To provide parking restrictions, street lighting and zebra crossings in village to improve perception of safety for children accessing school. |  |  | DPS | Access to school | [5 empty] | 145000 | 7105 | 152105 |  | 0 | 0
IT1396 | North Street, Nailsea dropped kerbs (Scrutiny schemes) | Review the whole length of the North Street for tactile pavers and dropped kerbs either there is not provision to get across to the Buchers in addition Hanham way has juction with no facilities (To be picked up as part of IT0861 (S106) Members priority scheme |  |  | TBA | Urban Active Travel | [9 empty] | 0 | 0
IT1281 | Pedestrian Facilities, Old Church Road, Clevedon (Scrutiny schemes) | To provide improved pedestrian access to the Salthouse Fields (Scrutiny Scheme ) |  |  | DPS | Urban Active Travel | [9 empty] | 0 | 0
IT1272 | The Woolpack, St. Georges (Scrutiny schemes) | To reduce the speed of traffic through the village and improve the safety of the roundabout (Members Priority Scheme) Incorporate IT1282 Speeding Issues Shepherds Way St Georges |  |  | TBA | Speed reduction | [9 empty] | 0 | 0
| Inflation/ contingency | To fund overspends | [7 empty] | 26641 | 50000 | 92038.13 | 4509.8684 | 168679.13 |  | 0 | -50000
[10 empty] | 191641 | 1035162 | 936038.13 | 45865.8684 | 2208706.9984 |  |  | -217432
[11 empty] | 123188.9984 |  |  |  |  | 20090.54 | -103098.4584 | KDH105 RS2503
[11 empty] | 0.12319 |  |  |  |  | 6404.53 | 6404.4068 | KDH105 RS2508
[16 empty] | 2000 | 2000 | KDH106 ST2508
[16 empty] | 22412 | 22412 | KDH103 PA2504
[16 empty] | 26193 | 26193 | KDH104 EC2504
-263521.0516
-7000
-270521.0516
Note on F2: Hilary D Crouch: vlookup from finance tab